## Introducción
Herramienta de autoevaluación de la disposición operativa para la introducción de la vacuna contra la COVID 19, versión actualizada (VIRAT/VRAF 2.0) Version al 3 de diciembre del 2020
1 | Esta herramienta de evaluación de la disposición operativa se aplica a nivel nacional. Los datos deben introducirse en la hoja 'Disposición operativa'. En el cronograma se presentan recomendaciones sobre fechas e intervalos para la ejecución de las actividades y la evaluacón del progreso.
2 | Las actividades preliminares de planificación debieron haberse iniciado incluso en septiembre del 2020 (el primer intervalo suministrado), puesto que puede haber vacunas contra la COVID-19 disponibles para su introducción a principios del 2021. La herramienta se actualizará en cuanto haya una mayor certeza sobre la disponibilidad del suministro de vacunas a nivel mundial.
3 | En la hoja de referencias (cuadro 2) puede encontrarse una lista de documentos técnicos y de planificación que puede usarse como guía para completar algunas de las actividades.
4 | Se incluye un cuadro con todas las equivalencias (cuadro 3) para facilitar la transición del VIRAT o el VRAF usados anteriormente a la nueva herramienta VIRAT/VRAF 2.0.
5 | En la nota informativa suministrada en el documento complementario puede encontrarse más información sobre la finalidad de esta herramienta y cómo usarla.

## Disposición operativa nacional
Country:
Nombre y organismo del funcionario que efectúa la revisión
Fecha de la revisión
Categoría | Actividades | Estado |  |  |  |  | Acción necesaria para llegar al estado de "concluidas" o "más del 90%" (las celdas grises indican que concluirlas es opcional) |  |  |  | Financiamiento
|  | Sept-20 oct (línea de base para la planificación previa) | Nov-20 dic | 21 ene | 21 feb | 21 mar | Acciones administrativas, organizativas, regulatorias y de coordinación a nivel central | Acciones administrativas, organizativas, regulatorias y de coordinación a nivel subnacional | Requisitos en materia de suministros médicos, equipos y servicios contractuales | Personal y capacitación necesarios | Financiamiento total necesario para llevar a cabo las acciones administrativas, adquirir los suministros y equipos médicos, y contratar y capacitar al personal para llegar al estado "concluidas" o "más del 90%"
A. PLANIFICACIÓN Y COORDINACIÓN | A.1 Establecer un comité coordinador nacional para la introducción de vacunas contra la COVID-19 o asignar esta tarea a un comité existente, con términos de referencia, funciones, responsabilidades y reuniones periódicas. El comité debe estar en funcionamiento y sus directivos deben rendir cuentas.
A.2 Establecer un grupo de trabajo técnico nacional para la introducción de vacunas contra la COVID-19 o asignar esta tarea a un grupo de trabajo existente, con términos de referencia, funciones, responsabilidades y reuniones periódicas.
A.3 Establecer subcomités del grupo de trabajo técnico nacional, de ser necesario, para los siguientes flujos de trabajo, o asignar esta tarea a subcomités existentes: 1) prestación de servicios; 2) vacuna, cadena de frío y logística; 3) generación de demanda y comunicación; 4) priorización, focalización y vigilancia de la COVID-19; 5) seguimiento y evaluación: determinación y comprobación de la elegibilidad, comprobante de vacunación, seguimiento de la cobertura de grupos de riesgo y seguimiento del impacto de la vacuna; 6) seguridad (abarca la prevención de lesiones, la detección de eventos adversos posvacunales y la respuesta a los mismos).
A.4 Orientar a los ministerios clave, a los comités asesores de prácticas de inmunización, a las partes interesadas y a los asociados sobre la introducción de vacunas contra la COVID-19 y las funciones previstas para cada uno. Difundir regularmente información y orientación de alcance mundial y regional (del Grupo de Expertos de la OMS en Asesoramiento Estratégico [SAGE] en materia de inmunización) por medio de los comités asesores de prácticas de inmunización tanto nacionales como regionales, y apoyar a los grupos de trabajo de los comités sobre vacunas contra la COVID-19.
A.5 Seleccionar y planificar el enfoque nacional del acceso a las vacunas y la compra (por ejemplo, Mecanismo COVAX, acuerdo bilateral de compra, adquisición por medio de un organismo de las Naciones Unidas, compras por cuenta propia), incluidos los costos de los artículos y los mecanismos de diligencia debida; indicar las necesidades clave, asegurar el cumplimiento regulatorio y efectuar los trámites requeridos. Asegurar que el plan de adquisiciones y la estrategia de compra abarquen las vacunas, los insumos auxiliares y el equipo de protección personal. Se ha aprobado el presupuesto, y los acuerdos de seguimientos están acordados y se actualizan según sea necesario.
A.6 Planificar y adquirir suministros y equipos de gestión de residuos para la aplicación adecuada de protocolos sobre este tema.
A.7 Asegurar que los objetivos del programa sean definidos y acordados por las partes interesadas clave a nivel central y subnacional, con la participación de representantes de los grupos poblacionales objetivo, líderes comunitarios y líderes religiosos, que reflejen la situación epidemiológica y que puedan adaptarse a las distintas situaciones de suministro de las vacunas (protección de grupos poblacionales vulnerables, continuidad de los servicios esenciales, equidad).
A.8 Elaborar el plan nacional de despliegue y vacunación con aportes de los organismos pertinentes (comité coordinador nacional de la respuesta a la COVID-19, centro nacional de control de la calidad, grupo de trabajo sobre ensayos clínicos, comités asesores de prácticas de inmunización, Programa Nacional de Inmunización, autoridad regulatoria nacional, comité sobre eventos adversos posvacunales y otros grupos pertinentes, como el sector privado). El plan nacional de despliegue y vacunación debe estar en consonancia con las orientaciones de la OMS y las recomendaciones del SAGE (el plan puede ser una adaptación del plan nacional de despliegue y vacunación para la gripe pandémica, si hay uno).
B. PRESUPUESTACIÓN | B.1 Incluir los costos del programa de vacunas contra la COVID-19 (vacuna, costos de operación, recursos humanos y gastos de capital) en los documentos presupuestarios o de planificación del gobierno aprobados por la autoridad correspondiente; además, incluir la consignación o asignación (del ministerio de hacienda o de tesorería) en la planificación del efectivo como medio adicional para asegurar que realmente haya fondos.
B.2 Comprobar que se hayan dispuesto los mecanismos de gestión de las asignaciones del ministerio de hacienda o de tesorería.
C. REGULACIÓN | C.1 Confirmar que haya una vía regulatoria rápida para la aprobación de vacunas contra la COVID-19 (es decir, autorización del uso de emergencia, aprobación excepcional o mecanismo de aprobación basado en la utilización o el reconocimiento de decisiones de otras autoridades regulatorias, procedimiento abreviado, vía rápida, etc.). Se deben indicar los plazos y el número máximo de días.
C.2 Asegurar que la autoridad regulatoria nacional u otra autoridad competente haya aclarado los requisitos regulatorios y los documentos necesarios para la aprobación de las vacunas contra la COVID-19 y los insumos conexos.
C.3 Asegurar que haya procedimientos regulatorios para el permiso de importación de vacunas contra la COVID-19 e insumos conexos, e indicar los requisitos y los documentos necesarios para su importación, incluso para el pago de impuestos y aranceles.
C.4 Confirmar a la OMS que hay un mecanismo de aprobación rápida de las importaciones por las autoridades competentes. Se deben indicar los plazos y el número máximo de días (plazo previsto: cinco días laborables como máximo).
C.5 Asegurar que se pueda autorizar el uso de las vacunas contra la COVID-19 (liberación de lotes) en menos de dos días, solamente con un examen del resumen del protocolo para el lote (sin exigir pruebas). Indicar los requisitos y los documentos necesarios para que las autoridades regulatorias nacionales liberen lotes de vacunas contra la COVID-19. Se deben indicar los plazos y el número máximo de días para la liberación de lotes o el proceso de exención.
D. PRIORIZACIÓN, FOCALIZACIÓN Y VIGILANCIA DE LA COVID-19 | D.1 Hacer el seguimiento del avance de los grupos de trabajo sobre vacunas contra la COVID-19 de los comités asesores de prácticas de inmunización y las recomendaciones provisionales sobre la priorización y los grupos de riesgo.
D.2 Determinar los posibles grupos poblacionales objetivo que tendrán acceso prioritario a las vacunas, estimar su número e indicar su ubicación geográfica, es decir, prepararse para definir e indicar el personal de salud que recibirá las vacunas y estimar su número.
D.3 Coordinar con el grupo nacional de vigilancia de la COVID-19 a fin de que se recopilen datos epidemiológicos pertinentes para fundamentar la planificación de rondas posteriores de vacunación, si corresponde, incluida la respuesta a brotes.
E. PRESTACIÓN DE SERVICIOS | E.1 Actualizar los protocolos de prevención y control de infecciones, incluido el equipo de protección personal (EPP) adecuado para reducir al mínimo el riesgo de exposición durante las sesiones de vacunación.
E.2 Seleccionar posibles estrategias para la administración de vacunas contra la COVID-19, así como estrategias de divulgación que aprovechen tanto las plataformas de vacunación existentes como los enfoques de los servicios que no impliquen vacunación para llegar mejor a los grupos objetivo indicados. Elaborar una lista maestra y una estrategia de prestadores de servicios, lugares de vacunación tanto fijos como móviles (por ejemplo, establecimientos de salud, centros comunitarios, mediante citas, casa por casa) y suministros médicos conexos para administrar eficazmente la vacuna contra la COVID-19 a los grupos poblacionales objetivo, y asegurar que se lleve a cabo la planificación necesaria para las ubicaciones y los aspectos logísticos.
E.3 Indicar los organismos a cargo de la implementación y celebrar acuerdos contractuales para preparar la introducción de las vacunas (por ejemplo, almacenamiento de vacunas, transporte, gestión de residuos, capacidad de la cadena de frío, etc.) cuando proceda. Para la administración por medio de establecimientos privados, elaborar y aprobar procedimientos estandarizados de trabajo que incluyan la calidad del servicio y el desempeño, así como normas y mecanismos para la presentación de informes, el manejo de quejas, la certificación de los establecimientos, el financiamiento, el seguimiento del desempeño y los controles de la integridad.
E.4 Asegurar que haya protocolos relativos al consentimiento para la vacunación, un procedimiento para la aceptación o el rechazo de la vacuna y medidas para proteger a las personas que se nieguen a vacunarse.
F. CAPACITACIÓN Y SUPERVISIÓN | F.1 Elaborar un plan de capacitación en todos los establecimientos participantes, a fin de prepararse para la introducción de vacunas contra la COVID-19, que abarque a grupos clave de participantes, áreas temáticas (entre ellas las prácticas de inyección seguras), asociados clave y métodos de capacitación (presencial o virtual). La OMS proporcionará una plantilla que servirá de guía.
F.2 Adaptar y traducir los materiales de capacitación elaborados por la OMS y preparar más materiales de acuerdo con el plan de capacitación.
F.3 Asegurar que haya planes para proteger al personal (por ejemplo, durante una emergencia o una campaña de gran alcance), las instalaciones de almacenamiento a escala central y regional y los productos en tránsito. Asegurar que haya normas aplicables al personal que llevará a cabo la vacunación, incluido todo el personal y los consultores que participen en tales actividades (y el personal militar, si procede), e indicar los requisitos relacionados con sustancias químicas, físicas y biológicas; la prohibición de la explotación, el abuso y el acoso sexuales; la participación en cursos; la presentación de informes y la prohibición de represalias.
F.4 Ofrecer cursos virtuales o presenciales según se indique en el plan de capacitación.
G. SEGUIMIENTO Y EVALUACIÓN | G.1 Establecer un marco de vigilancia y seguimiento o adaptar un marco existente con un conjunto de indicadores recomendados (cobertura, aceptabilidad, vigilancia de la enfermedad, etc.) para las vacunas contra la COVID-19, incluida la recopilación de información de establecimientos y contratistas que participen en la administración de vacunas, y asegurar que se cuente con los recursos humanos necesarios. Determinar si el registro y los informes serán individuales o combinados, así como la medida en que se puedan reutilizar las herramientas y los sistemas existentes.
G.2 Crear o adaptar las herramientas de seguimiento necesarias, sean electrónicas o en papel, y establecer mecanismos institucionales apropiados, como tarjetas o certificados de vacunación, registros nominales por establecimiento y hojas de recuento, informes de vacunación, registros médicos, registros de inmunización, sistemas de entrada de datos y herramientas analíticas para dar seguimiento al progreso y la cobertura de diferentes categorías de riesgo, y facilitar la administración de vacunas y la notificación oportuna.
G.3 Asegurar que se hayan adoptado medidas para la protección de los datos y normas adecuadas en materia de gestión de datos a fin de supervisar el uso y el procesamiento legítimos, adecuados y proporcionados de los datos que se recopilen regularmente y se manejen en los sistemas de información de salud.
G.4 Producir herramientas de seguimiento y distribuirlas a los prestadores que cumplan los requisitos para administrar vacunas; formular, probar y desplegar los cambios que sean necesarios en los sistemas electrónicos, y proporcionar capacitación para el uso de estas herramientas y procesos a prestadores tradicionales y nuevos.
G.5 Asegurar que se haya diseñado y puesto en marcha un mecanismo con múltiples puntos de entrada para recibir retroalimentación y quejas en relación con el programa de vacunación.
H. VACUNAS, CADENA DE FRÍO, ASPECTOS LOGÍSTICOS E INFRAESTRUCTURA | H.1 Establecer o fortalecer el grupo de trabajo nacional de logística con términos de referencia adecuados y procedimientos estandarizados de trabajo para coordinar el despliegue de vacunas contra la COVID-19 y productos auxiliares.
H.2 Hacer un mapeo de las funciones y responsabilidades clave necesarias para el despliegue de vacunas y productos auxiliares; recopilar información para contactar al personal y los establecimientos clave y confirmarla.
H.3 Crear una estrategia de distribución, con un mapeo de los posibles puertos de entrada, los lugares de almacenamiento (depósitos) y los establecimientos de reserva que haya en el país con su equipo de cadena de frío (de 2 a 8 ºC, -20 ºC, de -60 a -70 ºC) y la capacidad de transporte de vacunas y productos auxiliares, y asegurar que se cuente con los recursos humanos necesarios.
H.4 Elaborar un mapa y un plan para atender las necesidades de infraestructura, incluida la energía (energía primaria y de respaldo, especialmente para el equipo de cadena de frío), tecnología de la información y las comunicaciones (incluida la conexión a Internet) y agua.
H.5 Evaluar la capacidad de almacenamiento en seco y en cadena de frío, así como la infraestructura necesaria en todos los niveles, según las características de las vacunas contra la COVID-19, y resolver las brechas de suministro y logística detectadas.
H.6 Proporcionar a las partes interesadas pertinentes procedimientos estandarizados de trabajo (SOP por su sigla en inglés) apropiados para la COVID-19, así como protocolos o pautas para la recolección y eliminación de desechos médicos, tanto peligrosos como no peligrosos. Asegurar que haya prestadores de servicios de gestión de residuos debidamente autorizados (especialmente para el almacenamiento, el transporte y la eliminación de residuos peligrosos) y que estén listos para operar.
H.7 Actualizar e implementar sistemas y protocolos para el seguimiento y el monitoreo de la gestión y la distribución de las existencias de vacunas y suministros clave por medio del sistema de gestión e información logística de vacunas del gobierno, con procedimientos operativos que reflejen las características de las vacunas contra la COVID-19 (como el tamaño del vial y el indicador termosensible de los viales).
H.8 Difundir protocolos para la administración y la aceptación de vacunas, asegurar que haya mecanismos de seguimiento y designar puntos focales de supervisión en cada establecimiento. Establecer mecanismos para asegurar la integridad de las vacunas contra la COVID-19 y los productos auxiliares en toda la cadena de suministro.
I. VIGILANCIA DE LA SEGURIDAD | I.1 Asegurar que se hayan elaborado directrices, procedimientos documentados y herramientas para planificar y llevar a cabo actividades de farmacovigilancia de las vacunas (es decir, informes de eventos adversos posvacunales, investigación, evaluación de la causalidad, comunicación de riesgos y respuesta) y se los haya difundido en los establecimientos y sitios de vigilancia.
I.2 Asegurar que se cuente con recursos humanos adecuados y capacitados para llevar a cabo la vigilancia de eventos atribuibles a la vacunación.
I.3 Acelerar una representación adecuada, el establecimiento de términos de referencia bien definidos y la capacitación en lo que se refiere al comité de eventos adversos posvacunales para revisar los datos sobre seguridad de las vacunas contra la COVID-19 (por ejemplo, evaluación de la causalidad de eventos adversos posvacunales graves, conglomerados de eventos de este tipo y problemas de seguridad que estén surgiendo).
I.4 Determinar las disposiciones que exigen que los fabricantes ejecuten planes de gestión de riesgos, recopilen datos sobre la seguridad de las vacunas contra la COVID-19 y los presenten a la autoridad regulatoria nacional.
I.5 Planificar la vigilancia activa de eventos adversos específicos relacionados con vacunas contra la COVID-19. Si eso no es posible, elaborar disposiciones que permitan utilizar datos activos de vigilancia, decisiones e información de otros países u organismos regionales o internacionales.
I.6 Definir funciones y responsabilidades, y establecer un mecanismo de coordinación entre las partes interesadas pertinentes (autoridad regulatoria nacional, PAI, titulares de permisos de comercialización, ministerio de salud, OMS y otros) para el intercambio de información sobre la seguridad de las vacunas contra la COVID-19.
I.7 Seleccionar y asegurar canales para el intercambio de datos mediante los cuales se puedan dar a conocer datos y conclusiones sobre la seguridad de las vacunas contra la COVID-19 a los asociados regionales e internacionales pertinentes.
I.8 Establecer esquemas de compensación, como fondos de responsabilidad objetiva, por si las vacunas producen consecuencias no deseadas para la salud, y asegurar que se hayan adoptado las políticas correspondientes.
J. GENERACIÓN DE DEMANDA Y COMUNICACIÓN | J.1 Formular y difundir una estrategia de movilización y participación social o plan de demanda, así como un programa de concientización (que abarque tareas de promoción, comunicación, movilización social, comunicación de riesgos y seguridad, participación comunitaria y capacitación) para fomentar la confianza, promover la aceptación y la demanda de vacunas contra la COVID-19, y guiar la interacción con los medios de comunicación nacionales y locales, ONG, plataformas sociales, etc. Asegurar que en todos los niveles haya recursos humanos para la divulgación comunitaria y la gestión de la comunicación de riesgos que también explique la forma de presentar quejas y la manera en que se resolverán. Esta estrategia debe incluir la planificación de los preparativos para las comunicaciones en situaciones de crisis.
J.2 Establecer sistemas de recopilación de datos que incluyan: 1) seguimiento de las redes sociales y gestión de rumores, y 2) evaluación de datos sociales y de comportamiento.
J.3 Elaborar mensajes y materiales clave para la comunicación pública y la promoción, en consonancia con el plan de demanda.

## 2. Referencias
Inventario de documentos relacionados con la vacunación durante COVID-19
Diciembre del 2020
Documentos globales
Num | Category | Title | Date | Link | Type | Description | Issuing Dept
1 | 1. Planning for the deployment of COVID-19 vaccines | WHO Coronavirus Disease (COVID-19) Dashboard | Ongoing | https://covid19.who.int/ | Dashboard | Provides data on COVID-19 cases and deaths by country and by region | WHO Global
2 | 1. Planning for the deployment of COVID-19 vaccines | Draft landscape of COVID-19 candidate vaccines | 2020-10-02 | https://www.who.int/who-documents-detail/draft-landscape-of-covid-19-candidate-vaccines | Table | Provides information on the landscape of COVID-19 candidate vaccines. These landscape documents have been prepared by the World Health Organization (WHO) for information purposes only concerning the 2019-2020 global of the novel coronavirus. Inclusion of any particular product or entity in any of these landscape documents does not constitute, and shall not be deemed or construed as, any approval or endorsement by WHO of such product or entity (or any of its businesses or activities). | WHO Global
3 | 1. Planning for the deployment of COVID-19 vaccines | WHO Target Product Profiles for COVID-19 Vaccines | 2020-04-29 | https://www.who.int/publications/m/item/who-target-product-profiles-for-covid-19-vaccines#:~:text=This%20Target%20Product%20Profile%20(TPP,with%20rapid%20onset%20of%20immunity. | Technical document | This Target Product Profile (TPP) describes the preferred and minimally acceptable profiles for human vaccines for long term protection of persons at high ongoing risk of COVID-19 such as healthcare workers and for reactive use in outbreak settings with rapid onset of immunity. | WHO Global
4 | 1. Planning for the deployment of COVID-19 vaccines | Fair allocation mechanism for COVID-19 vaccines through the COVAX Facility | 2020-09-09 | https://www.who.int/publications/m/item/fair-allocation-mechanism-for-covid-19-vaccines-through-the-covax-facility | Technical document | The ACT-Accelerator was set up to contain the COVID-19 pandemic faster and more efficiently by ensuring that successful diagnostics, vaccines and treatments are shared equitably across all countries. Key to achieving that goal is the design and implementation of a Fair Allocation Framework. | WHO Global
5 | 1. Planning for the deployment of COVID-19 vaccines | WHO SAGE values framework for the allocation and prioritization of COVID-19 vaccination | 2020-09-13 | https://www.who.int/publications/i/item/who-sage-values-framework-for-the-allocation-and-prioritization-of-covid-19-vaccination | Technical document | This Values Framework offers guidance globally on the allocation of COVID-19 vaccines between countries, and to offer guidance nationally on the prioritization of groups for vaccination within countries while supply is limited. The Framework is intended to be helpful to policy makers and expert advisors at the global, regional and national level as they make allocation and prioritization decisions about COVID-19 vaccines. This document has been endorsed by the Strategic Advisory Group of Experts on Immunization (SAGE). | IVB
6 | 1. Planning for the deployment of COVID-19 vaccines | WHO SAGE roadmap for prioritizing uses of COVID-19 vaccines in the context of limited supply | 2020-11-13 | https://www.who.int/docs/default-source/immunization/sage/covid/sage-prioritization-roadmap-covid19-vaccines.pdf?Status=Temp&sfvrsn=bf227443_2&ua=1 | Technical document | Given the urgency and wide-ranging effects of the COVID-19 pandemic, SAGE has developed an approach to help inform deliberation around the range of recommendations that may be appropriate under different epidemiologic and vaccine supply conditions | IVB
7 | 1. Planning for the deployment of COVID-19 vaccines | Guidance on developing a national deployment and vaccination plan for COVID-19 vaccines | 2020-11-16 | https://www.who.int/publications/i/item/WHO-2019-nCoV-Vaccine_deployment-2020.1 | Guidelines | The Guidance on National Deployment and Vaccination Planning is intended to help countries develop their plan for COVID-19 vaccine introduction. | IVB
8 | 1. Planning for the deployment of COVID-19 vaccines | COVAX on Gavi website | Ongoing | https://www.gavi.org/covax-facility#:~:text=COVAX%20is%20co%2Dled%20by,every%20country%20in%20the%20world. | Website | COVAX is co-led by Gavi, the Coalition for Epidemic Preparedness Innovations (CEPI) and WHO. Its aim is to accelerate the development and manufacture of COVID-19 vaccines, and to guarantee fair and equitable access for every country in the world. | Gavi
9 | 1. Planning for the deployment of COVID-19 vaccines | WHO documents on pandemic preparedness and pandemic vaccine deployment | Various | https://www.who.int/influenza/preparedness/pandemic/en/ | Website | WHO guidance and documents on pandemic preparedness and vaccine deployment. | WHO Global
10 | 1. Planning for the deployment of COVID-19 vaccines | Active surveillance of adverse events | 2020-07-10 | https://apps.who.int/iris/bitstream/handle/10665/333136/WER9528-eng-fre.pdf?ua=1 | WHO WER | Global Advisory Committe on Vaccine Safety, WHO Weekely Epidemiological Record | WHO Global
11 | 1. Planning for the deployment of COVID-19 vaccines | COVID-19 Vaccines: Safety Surveillance Manual Module: Establishing surveillance systems in countries using COVID-19 vaccines | Ongoing | https://www.who.int/vaccine_safety/committee/Module_Establishing_surveillance_systems.pdf?ua=1 | Guidelines | Vaccine Safety Surveillance guidelines | WHO Global
12 | 2. Immunization programme in the context of COVID-19 | Immunization as an essential health service: guiding principles for immunization activities during the COVID-19 pandemic and other times of severe disruption | 2020-11-10 | https://www.who.int/publications/i/item/immunization-as-an-essential-health-service-guiding-principles-for-immunization-activities-during-the-covid-19-pandemic-and-other-times-of-severe-disruption | Technical document | This document, endorsed by the WHO Strategic Advisory Group of Experts on Immunization, provides guiding principles to support countries in their decision-making regarding provision or resumption of immunization services during severe disruptive events such as COVID-19, natural disasters or humanitarian emergencies. It incorporates the Immunization Agenda 2030 principles of being people-centred, country-owned, partnership-based and data-guided | IVB
13 | 2. Immunization programme in the context of COVID-19 | FAQs: Immunization in the context of COVID-19 pandemic | 2020-04-16 | https://www.who.int/publications-detail/immunization-in-the-context-of-covid-19-pandemic | FAQ | These FAQs accompany WHO’s Guiding principles for immunization activities during the COVID-19 pandemic | IVB
14 | 2. Immunization programme in the context of COVID-19 | Infection Prevention and Control guidance for Long-Term Care Facilities in the context of COVID-19 | 2020-03-21 | https://apps.who.int/iris/bitstream/handle/10665/331508/WHO-2019-nCoV-IPC_long_term_care-2020.1-eng.pdf | Interim Guidance | Provide annual influenza vaccination and pneumococcal conjugate vaccines to employees and staff, according to local policies, as these infections are important contributors to respiratory mortality in older people. | IPC/HQ
15 | 2. Immunization programme in the context of COVID-19 | Mask use in the context of COVID-19 | 2020-12-01 | https://www.who.int/publications/i/item/advice-on-the-use-of-masks-in-the-community-during-home-care-and-in-healthcare-settings-in-the-context-of-the-novel-coronavirus-(2019-ncov)-outbreak | Interim Guidance | This document provides updated guidance on mask use in health care and community settings, and during home care for COVID-19 cases. It is intended for policy makers, public health and infection prevention and control professionals, health care managers and health workers. The Annex provides advice on how to manufacture non-medical masks. It is intended for those making non-medical masks at home and for mask manufacturers. | IPC/HQ
16 | 2. Immunization programme in the context of COVID-19 | Community-based health care, including outreach and campaigns,in the context of the COVID-19 pandemic | 2020-05-05 | https://apps.who.int/iris/handle/10665/331975 | Interim Guidance | Immunization module is a module (page 31), among other essential health services .This joint WHO, UNICEF and IFRC guidance addresses the role of community-based health care in the pandemic context. It includes practical recommendations for decision makers to help keep communities and health workers safe, to sustain essential services at the community level, and to ensure an effective response to COVID-19. Using this comprehensive and coordinated approach will help countries strengthen the resilience of community-based health services throughout the pandemic, into early recovery and beyond. | Integrated Health Services
17 | 2. Immunization programme in the context of COVID-19 | Considerations for school-related public health measures in the context of COVID-19. Annex to Considerations in adjusting public health and social measures in the context of COVID-19 | 2020-05-10 | https://apps.who.int/iris/handle/10665/332052 | Annex to Considerations in adjusting public health and social measures in the context of COVID-19 | Ensure that school entry immunization checks are in place. Check vaccination status for outbreak-prone vaccine preventable diseases (e.g. measles) and remind parents of the importance of ensuring their children are up to date with all eligible vaccinations. For school-based immunization programmes, ensure there a plan for catch-up vaccination if needed. | MCA
18 | 2. Immunization programme in the context of COVID-19 | Temperature-sensitive health products in the expanded programme on immunization cold chain: a WHO-UNICEF joint statement encouraging greater health commodity supply chain integration for temperature-sensitive pharmaceuticals where appropriate | 2020-11-19 | https://apps.who.int/iris/handle/10665/336748 | Interim Guidance | The WHO and United Nations Children’s Fund (UNICEF), reiterate the value of safe, feasible, and cost-effective integration of temperaturesensitive health products into the Expanded Programme on Immunization (EPI) health supply chains. This interim guidance provides further clarity by highlighting integration as a practical solution and provides reference to planning tools to design and implement an integrated cold chain. | IVB
19 | 2. Immunization programme in the context of COVID-19 | COVID-19 Vaccination, Country Readiness and Delivery: Supply and Logistics Guidance | 2020-11-30 | https://www.technet-21.org/en/library/main/6717-covid-19-vaccination,-country-readiness-and-delivery:-supply-and-logistics-guidance | Interim Guidance | The COVAX Supply and Logistics workstream lead by UNICEF, Gavi and WHO have released a working copy of the COVID-19 Vaccination, Country Readiness & Delivery: Supply and Logistics Guidance. Countries might find this Guide useful when developing and strengthening their supply chain strategies to receive, store, distribute and manage the COVID-19 vaccines and their ancillary products, in line with their national deployment and vaccination plan (NDVP). The document also provides links to the different tools and resources to aid countries in performing assessment, planning and capacity-building activities | WHO/UNICEF
20 | 2. Immunization programme in the context of COVID-19 | Framework for Decision-Making: Implementation of mass vaccination campaigns during the COVID-19 pandemic | 2020-05-22 | https://apps.who.int/iris/handle/10665/332159 | Interim Guidance | In the context of the COVID-19 pandemic, this document: I.Outlines a common framework for decision-making for the conduct of preventive and outbreak response campaigns II. Offers principles to consider when deliberating the implementation of a mass vaccination campaigns for prevention of increased risk of VPD/HID among susceptible populations; III. Details risks and benefits of conducting outbreak-response vaccination campaigns to respond to VPD/HID outbreaks. | IVB
21 | 2. Immunization programme in the context of COVID-19 | Bacille Calmette-Guérin (BCG) vaccination and COVID-19 | 2020-04-12 | https://www.who.int/publications-detail/bacille-calmette-gu%C3%A9rin-(bcg)-vaccination-and-covid-19 | Scientific Brief | There is no evidence that the Bacille Calmette-Guérin vaccine (BCG) protects people against infection with COVID-19 virus. Two clinical trials addressing this question are underway, and WHO will evaluate the evidence when it is available. In the absence of evidence, WHO does not recommend BCG vaccination for the prevention of COVID-19. WHO continues to recommend neonatal BCG vaccination in countries or settings with a high incidence of tuberculosis. | IVB
22 | 3. COVID-19 response | Monitoring and Evaluation Framework COVID‑19 Strategic Preparedness and Response (SPRP) | 2020-05-22 | https://www.who.int/publications-detail/monitoring-and-evaluation-framework | Guidelines | The COVID 19 Strategic Preparedness and Response Plan (SPRP) Monitoring and Evaluation Framework (COVID 19 M&E Framework) lists key public health and essential health services and systems indicators to monitor preparedness, response, and situations during the COVID 19 pandemic. Indicators have been grouped around nine pillars and one thematic area. Immunization indicators, in the ninth pillar - Maintaining essential health services and systems include (i) DTP3 vaccination coverage in children under 12 months of age (ii) Percentage of countries where at least one VPD-immunization campaign was affected (suspended or postponed partially or fully) by COVID 19. | WHO Global
23 | 3. COVID-19 response | Clinical management of COVID-19 | 2020-05-27 | https://www.who.int/publications-detail/clinical-management-of-covid-19 | Interim Guidance | At the time of discharge, the patient’s ongoing primary health care needs should be reviewed, including ensuring an up-to-date immunization status. This is especially important for children who may have missed immunizations. If needed, individuals should be offered referrals for immunization services. | Clinical Group /HQ
24 | 3. COVID-19 response | Maintaining essential health services in the COVID-19 context: Implementing the WHO operational guidance | 2020-06-01 | https://www.who.int/publications/i/item/WHO-2019-nCoV-essential-health-services-2020.1 | Interim Guidance | This document expands on the original operational guidance on maintaining essential health services during an outbreak. It provides implementation guidance on a set of targeted immediate actions that countries should consider at national, sub-national and local levels to reorganize and maintain access to high-quality, essential health services. This document outlines needed adaptations to keep people safe, maintain continuity of essential services, and ensure effective response to COVID-19. | Integrated Health Services
25 | 3. COVID-19 response | Continuity of essential health services: Facility assessment tool | 2020-11-20 | https://www.who.int/publications-detail-redirect/WHO-2019-nCoV-HCF_assessment-EHS-2020.1 | Interim Guidance | The Continuity of essential health services: Facility Assessment Tool can be used by countries to rapidly assess the capacity of health facilities to maintain the provision of essential health services during the COVID-19 pandemic. It can help to alert the authorities and other stakeholders about where service delivery and utilization may require modification and/or investment | Essential Health Services
26 | 3. COVID-19 response | Maintaining surveillance of influenza and monitoring SARS-CoV-2: adapting Global Influenza Surveillance and Response System (‎GISRS)‎ and sentinel systems during the COVID-19 pandemic | 2020-11-08 | https://apps.who.int/iris/handle/10665/336689?show=full | Interim Guidance | This document is an update of the interim guidance entitled Operational considerations for COVID-19 surveillance using GISRS, published on 26 March 2020, and of the interim guidance Preparing GISRS for the upcoming influenza seasons during the COVID-19 pandemic – practical considerations, published on 26 May 2020 | WHO Global
27 | 4. Polio programme in the context of COVID-19 | Polio Eradication Programme continuity planning measures to ensure continuity of operations in the context of the COVID-19 pandemic (May 2020) | May 2020 (update) | http://polioeradication.org/wp-content/uploads/2020/03/COVID-POL-programme-continuity-planning-20200325.pdf | Interim Guidance | The purpose of this document is to provide guidance to polio programme continuity planning in the context of the COVID-19 pandemic. Its intended users are the polio programme planners and managers in the GPEI target countries and regional offices. Considering the global nature of the polio eradication programme, it also provides recommendations for the areas of work relevant to the global level planning. | Polio
28 | 4. Polio programme in the context of COVID-19 | Interim Guidance for the Polio Surveillance Network in the context of Coronavirus (COVID 19) | 2020-06-04 | https://www.who.int/publications/i/item/WHO-POLIO-20.04 | Interim Guidance | The document aims to provide global guidance to Polio Surveillance activities in the context of the COVID 19 pandemic. It comes as a complement of the Polio Eradication Programme continuity Planning and aligns with the full support that the GPEI has announced to the COVID 19 pandemic. | Polio
29 | 4. Polio programme in the context of COVID-19 | Interim Guidance for Frontline Workers on Safe Implemenation of H-T-H Vaccination campaigns t (COVID 19) | 2020-06-25 | http://polioeradication.org/wp-content/uploads/2020/03/Interim-guidelines-for-frontline-workers-on-safe-implementation-of-house-to-house-vaccination-campaigns.pdf | Interim Guidance | The purpose of this document is to provide specific guidance to national and sub-national programme managers who will be supporting frontline workers for the safe implementation of house-to-house polio immunization campaigns in the context of the COVID-19 pandemic. | Polio
30 | 5. Regional Documents | Immunization in the context of the SARS-COV2 (COVID-19) pandemic Operational guidelines for National Immunization Programs in the WHO African Region IVD program, WHO AFRO | 2020-04-21 | https://lnct.global/wp-content/uploads/2020/05/WHO-AFRO_Operational-guidance-on-Immunisation-in-the-context-of-the-COVID-19-pandemic_21-April-2020.pdf | Interim Guidance | These guidelines are intended to operationalize the global guidance on immunization during COVID-19 pandemic in the African Region and attempt to outline the key principles and the recommended activities for National Immunization Programs (NIP) to mitigate the risks posed by the COVID-19 pandemic. These guidelines will be regularly revised and updated as the epidemiological situation of COVID-19 evolves. The guidelines are expected to be used by NIP, local partners, and stakeholders involved in the planning, implementation and monitoring & evaluation of immunization and vaccine preventable disease control programs. | IVD/AFRO
31 | 5. Regional Documents | Guidance on routine immunization services during COVID-19 pandemic in the WHO European Region | 2020-03-20 | http://www.euro.who.int/en/health-topics/communicable-diseases/hepatitis/publications/2020/guidance-on-routine-immunization-services-during-covid-19-pandemic-in-the-who-european-region,-20-march-2020 | Interim Guidance | The current COVID-19 situation and health system capacities vary widely across the WHO European Region, and this situation is rapidly evolving. Approaches to sustain high levels of routine immunization coverage will also vary among countries. In planning these measures, due consideration should be given to minimizing the excess risk of morbidity and mortality from vaccine-preventable diseases (VPDs) that would result if immunization services are disrupted. This guidance provides all possible efforts that should be made by the Ministry of Health to equitably sustain high population immunity. | EURO
32 | 5. Regional Documents | Routine immunization services during the COVID-19 pandemic | 2020-04-13 | https://apps.who.int/iris/handle/10665/331925 | Interim Guidance | This document provides guidance to Member States on how to prioritize and adapt immunization services during the Covid-19 pandemic, and steps to mitigate the impact of the pandemic on vaccine-preventable diseases. | WPRO
33 | 5. Regional Documents | The Immunization Program in the Context of the COVID-19 Pandemic. Version 1 | 2020-03-26 | https://www.paho.org/en/documents/immunization-program-context-covid-19-pandemic-march-2020 | Interim Guidance | This document provides guidance regarding the operation of immunization programs in the context of the COVID-19 pandemic. It contains recommendations on vaccination and epidemiological surveillance for vaccine- preventable diseases (VPDs) in the context of the COVID-19 pandemic, in the Region of the Americas, which were consulted on by members of PAHO’s Technical Advisory Group (TAG) on Vaccine-preventable Diseases, and are aligned with recommendations from WHO’s Strategic Advisory Group of Experts (SAGE) on immunization. | PAHO
34 | 5. Regional Documents | The Immunization Program in the Context of the COVID-19 Pandemic. Version 2 | 2020-04-24 | https://www.paho.org/en/documents/immunization-program-context-covid-19-pandemic-version-2-24-april-2020 | Interim Guidance | Objective: Provide guidance regarding the operation of immunization programs in the context of the COVID-19 pandemic.This publication updates the previous publication from 26 March 2020. | PAHO
35 | 5. Regional Documents | Vaccination of Newborns in the Context of the COVID-19 Pandemic | 2020-05-19 | https://www.paho.org/en/documents/vaccination-newborns-context-covid-19-pandemic-19-may-2020 | Interim Guidance | These preliminary recommendations provide guidance regarding vaccination of newborns with hepatitis B and BCG vaccines in the context of the COVID-19 pandemic, in order to maintain high vaccination coverage. | PAHO
36 | 5. Regional Documents | Immunization throughout the Life Course at the Primary Care Level in the Context of the COVID-19 Pandemic | 2020-06-17 | https://www.paho.org/en/documents/immunization-throughout-life-course-primary-care-level-context-covid-19-pandemic | Interim Guidance | Provide recommendations regarding vaccination as an essential service at the primary care level in the context of the COVID-19 pandemic. | PAHO

## 3. Equivalencias
Cuadro de equivalencias de los códigos de los indicadores en la herramienta nueva (VIRAT/VRAF 2.0) y las herramientas anteriores (VIRAT y VRAF)
Category | Código de los indicadores VIRAT/VRAF 2.0 | Código de los indicadores VIRAT | Código de los indicadores VRAF
A. PLANIFICACIÓN Y COORDINACIÓN | A.1 | A.1 | A.1.4
| A.2 | A.2
| A.3 | A.3
| A.4 | A.4, A.5
| A.5 | A.7 | B.1.1, B.1.2
| A.6 |  | B.1.3
| A.7 |  | A.1.1
| A.8 | A.6
B. PRESUPUESTACIÓN | B.1 | B.1, B.2, B.3, B.4 | A.4.1
| B.2 | B.1, B.2, B.3, B.4 | A.4.2
C. REGULACIÓN | C.1 | C.1
| C.2 | C.2 | A.2.1
| C.3 | C.3 | A.2.2, A.2.3
| C.4 | C.4
| C.5 | C.5
D. PRIORIZACIÓN, FOCALIZACIÓN Y VIGILANCIA DE LA COVID-19 | D.1 | D.1
| D.2 | D.2 | A.1.3
| D.3 | D.3
E. PRESTACIÓN DE SERVICIOS | E.1 | E.1 | B.1.2
| E.2 | E.2, E.3 | A.3.2, B.2.1 C.2.1
| E.3 | H.5 | A.2.8, A.1.2
| E.4 |  | A.2.6
F. CAPACITACIÓN Y SUPERVISIÓN | F.1 | F.1 | C.2.3
| F.2 | F.2
| F.3 | E.4 | A.2.7
| F.4 | F.3
G. SEGUIMIENTO Y EVALUACIÓN | G.1 | G.1 | A.3.5
| G.2 | G.2 | D.1.1, C.2.2
| G.3 |  | A.2.4
| G.4 | G.3
| G.5 |  | A.3.4
H. VACUNAS, CADENA DE FRÍO, ASPECTOS DE LOGÍSTICA E INFRAESTRUCTURA | H.1 | H.1
| H.2 | H.2
| H.3 | H.3 | B.2.1, B.2.2
| H.4 |  | D.2.1, D.2.2
| H.5 | H.4 | A.3.1, B.2.2
| H.6 | H.6 | B.3.1, B.3.2, B.3.3
| H.7 | H.7 | B.2.3
| H.8 | H.8 | C.2.4
I. VIGILANCIA DE LA SEGURIDAD | I.1 | I.1 | C.3.1
| I.2 | I.2 | C.3.1
| I.3 | I.3 | C.3.2
| I.4 | I.4
| I.5 | I.5
| I.6 | I.6
| I.7 | I.7
| I.8 |  | A.2.5, C.3.3
J. GENERACIÓN DE DEMANDA Y COMUNICACIÓN | J.1 | J.1 | C.1.1
| J.2 | J.2 | C.1.2
| J.3 | J.3 | C.1.3

## VIRAF Tool (hidden)
Vaccine Introduction Readiness Assessment Framework (VIRAF)
Nombre y organismo del funcionario que efectúa la revisión
Fecha de la revisión
Categoría | Activities (Red shaded activities are WHO pre-planning activities) | WHO Pre-planning activity | Estado (las celdas amarillas indican el plazo para la finalización de la actividad; las celdas verdes indican las actividades que deben realizarse en los plazos correspondientes al país) |  |  |  | Process |  |  |  | Administrative, organizational, legislative/regulatory and coordination requirements (Gray cells are for optional completion) | [5 empty] | Medical supplies and supporting infrastructure equipment and transport (Gray cells are for optional completion) |  |  |  | Human resources and training (Gray cells are for optional completion) |  |  |  | Financiamiento (las celdas grises indican que la conclusión es opcional) | Outputs/Comments
[11 empty] | Central |  |  | Sub-National: Departments, Regions, Districts
|  |  | Sept-oct 20 (línea de base para la planificación previa) | Nov-dic 20 | Dic 20-ene 21 | Feb-mar 21 | If activity not completed, give reason | Action required | Deadline | Person responsible MoH & TA partners (as relevant) | Brief assessment of current status | What administrative, organizational, regulatory and coordination actions need to be undertaken to get to 'completed' or 'more than 90%' status | What would it cost to undertake the administrative, organizational, regulatory and coordination actions to get to 'completed' or 'more than 90%' status | Brief assessment of current status | What administrative, organizational, regulatory and coordination actions need to be undertaken to get to 'completed' or 'more than 90%' status | What would it cost to undertake the administrative, organizational, regulatory and coordination actions to get to 'completed' or 'more than 90%' status | What medical supplies and equipment are needed to get to 'completed' of 'more than 90%' status | What is currently available | What medical supplies and equipment need to be procured to meet the shortfall | What would it cost to procure the medical supplies and equipment to get to 'completed' or 'more than 90%' status | What are the staffing and training requirements to get a 'completed' or 'more than 90%' status | What is currently available | What staff needs to be hired and trained to meet the shortfall | What would it cost to hire and train staff needed to get to 'completed' or 'more than 90%' status | What is the total financing needed to undertake the administrative actions, procure the medical supplies and equipment, and hire and train staff to get to a 'completed' or 'more than 90%' status
A. PLANIFICACIÓN Y COORDINACIÓN | A.1 Establecer un Comité Coordinador Nacional (CCN) para la introducción de vacunas contra la COVID-19, o asignar esta tarea a un comité existente, con términos de referencia, funciones, responsabilidades y reuniones periódicas. El comité debe estar en funcionamiento y sus directivos deben rendir cuentas. | Yes | [22 empty] | 0 | NCC is established/engaged
| A.2 Establish (or engage an existing working group) a National Technical Working Group (NTWG) for COVID-19 vaccine introduction with terms of reference, roles and responsibilities and regular meetings | Yes | [22 empty] | 0 | NTWG is established/engaged
| A.3 Establish or engage existing NTWG subcommittees, if required, to cover the following workstreams: 1) service delivery 2) vaccine, cold chain & logistics, 3) demand generation & communication (4) prioritization, targeting and COVID-19 surveillance, (5) Monitoring and Evaluation: determination and proof of eligibility, proof of vaccination, monitoring of coverage among at-risk groups, and monitoring of vaccine impact (6) Safety, including injury prevention and AEFI detection and response | [23 empty] | 0 | NTWG subcommittees engaged for: 1) service delivery 2) vaccine, cold chain & logistics, 3) demand generation & communication (4) prioritization, targeting and COVID-19 surveillance, (5) Monitoring and Evaluation: determination and proof of eligibility, proof of vaccination, monitoring of coverage among at-risk groups, and monitoring of vaccine impact (6) Safety, including injury prevention and AEFI detection and response
| A.4 Brief key ministries, NITAG, stakeholders and partners about COVID-19 vaccine introduction and their expected roles | [23 empty] | 0 | Key ministries, stakeholders, partners, and NITAG briefed on vaccine introduction and expected roles
| A.5 Ensure that program objectives are defined and agreed to by key stakeholders at the central and sub-national levels, and reflect the epidemiological situation and are adaptable to vaccine supply scenarios (protection of vulnerable populations, continuity of essential services, equity) | [23 empty] | 0 | Program objectives defined and agreed on
| A.6 Inform regularly & disseminate global and regional guidance (i.e. SAGE) with NITAGs & RITAGs and support NITAG working groups on COVID-19 vaccines | [23 empty] | 0 | Global/regional guidance regularly disseminated
| A.7 Develop the National Deployment and Vaccination Plan (NDVP) with input from relevant bodies (National COVID-19 Response Coordinating Committee, CNCC, CTWG, NITAG, National Immunization Programme, National Regulatory Authority, AEFI committee and other relevant groups such as private sector). The NDVP should be in line with WHO guidance and SAGE recommendations (plan can be developed by adapting the Pandemic Influenza NDVP, if existing) | [23 empty] | 0 | NDVP developed
| A.8 Identify and plan for the national vaccine access/procurement approach (e.g. COVAX Facility, bilateral purchase agreement, procurement through UN agency, self-procurement), identify key needs, ensure regulatory compliance, and complete required paperwork. Ensure that the procurement plan and purchasing strategy includes vaccines, ancillary supplies, and Personal Protective Equipment | [23 empty] | 0 | Procurement plan/vaccine access plan developed, key needs identified, paperwork completed
| A.9 Plan and procure waste management supplies and equipment for appropriate implementation of waste management protocols | [23 empty] | 0 | Waste management plan complete, supplies procured
| A.10 Review and prepare Government signature for legal agreement to receive Covid-19 vaccine | [23 empty] | 0 | Legal agreements signed by government
B. RESOURCES & FUNDING | B.1 Estimate financial and human resources needed (including surge capacity requirements) to conduct the deployment and vaccination operations in the designated points and in the required number of days | [23 empty] | 0 | Financial and human resources needed estimated
| B.2 Identify funding mechanisms and prepare a resource map in collaboration with relevant stakeholders including Inter-Agency Coordinating Committee (ICC), if available at country | [23 empty] | 0 | Funding mechanisms identified
| B.3 Finalize the budgeted micro-plans for vaccination including plans for other relevant components such as demand generation, risk communications and safety surveillance, and ensure that all COVID-19 vaccine program costs have been included in government budgetary and planning documents approved by the appropriate authority | [23 empty] | 0 | Budgeted micro-plans finalized, included in government budgeting and planning documents, and approved by government
C. REGLAMENTACIÓN | C.1 Confirmar la existencia de una vía regulatoria acelerada para la aprobación de vacunas contra la COVID-19 (es decir, autorización del uso de emergencia, aprobación excepcional o mecanismo de aprobación basado en la utilización o el reconocimiento de decisiones de otras autoridades regulatorias, procedimiento abreviado, vía rápida, etc.). Se deben indicar los marcos cronológicos y el número máximo de días. | Yes | [22 empty] | 0 | Any expedited regulatory pathways identified and confirmed
| C.2 Ensure the national regulatory authority or other concerned authority has clarified the regulatory requirements, and documents needed for regulatory approvals of COVID-19 vaccines and related supplies | [23 empty] | 0 | Regulator has clarified regulatory requirements and documents
| C.3 Asegurar que haya procedimientos reglamentarios para el permiso de importación de vacunas contra la COVID-19 y suministros conexos, e indicar los requisitos y los documentos necesarios para importar vacunas contra la COVID-19 y suministros conexos, incluso para los impuestos y aranceles. | [23 empty] | 0 | Import regulations/requirements are in place and clarified, including for taxes and tariffs
| C.4 Confirm to WHO the existence of an expedited import approval from appropriate authorities. Time lines and maximum number of days should be mentioned. (expected timeline: maximum 5 working days) | [23 empty] | 0 | Any expedited import approval identified and confirmed to WHO
| C.5 Ensure COVID-19 vaccines can be released (lot release) in less than two days by reviewing the summary lot protocol only (testing is not required)? Identify the requirements and documents needed for NRA lot release for COVID-19 vaccines. Time lines and maximum number of days for lot release/waiver process should be mentioned. | [23 empty] | 0 | System to waive local lot release testing in place
D. PRIORIZACIÓN, FOCALIZACIÓN Y VIGILANCIA DE LA COVID-19 | D.1 Monitor progress of NITAG working groups on COVID-19 vaccines and interim recommendations focusing on prioritization and risk groups | Yes | [22 empty] | 0 | Ongoing progress of NITAG working groups is being monitored
| D.2 Identify potential target populations that will be prioritized for access to vaccines, estimate their numbers, and identify their geographic location, i.e. prepare first to define, identify and estimate no. of HCWs | [23 empty] | 0 | Target populations identified and enumerated
| D.3 Coordinate with national COVID-19 disease surveillance group to ensure relevant epidemiological data will be collected to inform planning of subsequent rounds of COVAX vaccination, including outbreak responses. | [23 empty] | 0 | Epidemiological data collection for planning purposes is planned for in partnership with national COVID-19 disease surveillance group
E. Prestación de servicios | E.1 Update protocols for infection prevention and control measures including adequate personal protection equipment (PPE) to minimize exposure risk during immunization sessions | Yes | [22 empty] | 0 | Protocols for infection prevention (including PPE) are updated
| E.2 Conduct a gap analysis of delivery capacity, and identify potential bottlenecks, capacity deficiencies and recommendations for improvement | [23 empty] | 0 | Gap analysis of delivery capacity completed
| E.3 Identify and implement potential COVID-19 vaccine delivery strategies and outreach strategies leveraging both existing vaccination platforms and non-vaccination delivery approaches to best reach identified target groups. Ensure that the necessary planning for locations and logistics is carried out | [23 empty] | 0 | Vaccine outreach and delivery strategies to reach target groups identified and implemented
| E.4 Identify and develop a master list and strategy of service providers, points of delivery, including fixed and outreach (e.g. health facilities, community centers, by appointments, house-to-house) and associated medical supplies that could effectively deliver COVID-19 vaccine to target populations | [23 empty] | 0 | Master list of service providers, points of delivery, and medical supplies identified and developed
| E.5 For delivery through private facilities, ensure that Standard Operating Procedures are developed, a mechanism for certification of facilities is approved, a financing mechanism is developed and a mechanism for monitoring of performance and service quality is agreed | [23 empty] | 0 | SOPs for private facilities delivering vaccine are developed
| E.6 Ensure availability of plans to safeguard the security of staff (e.g. during an emergency or major campaign) as well as security at the central and/or regional storage facilities and for in-transit of products | [23 empty] | 0 | Staff security plans established and implemented
| E.7 Ensure that appropriate institutional and electronic management systems (medical records, systems entry, immunization cards) that facilitate successful delivery of vaccines are in place to allow timely and accurate reporting on delivery, and adequate and trained human resources are available | [23 empty] | 0 | Institutional and electronic management systems to track vaccinations (medical records, immunization cards, etc) are implemented, and staff training is complete
| E.8 Ensure existence of protocols regarding consent to vaccinations, process for agreeing to or refusing to be vaccinated, and measures to protect those that refuse to be vaccinated are in place | [23 empty] | 0 | Regulations on consent to vaccinations and protections for those that refuse to be vaccinated are in place
| E.9 Ensure regulations are in place regarding personnel who will be carrying out vaccinations, including all staff/personnel/consultants etc. engaged in such activities (cover military personnel also, if possible), and include requirements relating to chemical, physical and biological substances, not engaging in sexual exploitation and abuse and sexual harassment, participation in training, reporting and non-retaliation | [23 empty] | 0 | Regulations for personnel carrying out vaccinations are in place, including requirements relating to chemical, physical and biological substances, not engaging in sexual exploitation and abuse and sexual harassment, participation in training, reporting and non-retaliation
F. CAPACITACIÓN Y SUPERVISIÓN | F.1 Develop a training plan across all participating facilities to prepare for COVID-19 vaccine introduction that includes key groups of participants, content topic areas (including safe injection practices), key training partners and training methods (in-person or virtual). WHO will provide a template for guidance | Yes | [22 empty] | 0 | Training plan developed
| F.2 Adapt and translate training materials developed by WHO and develop additional training materials as outlined in the training plan | [23 empty] | 0 | Training materials developed, adapted and translated
| F.3 Delivery protocols have been disseminated and supervisory focal points at each facility identified and properly trained | [23 empty] | 0 | Delivery protocols distributed, focal points identified and trained
| F.4 Conduct virtual and/or in person trainings as outlined in the training plan | [23 empty] | 0 | Trainings completed
G. SEGUIMIENTO Y EVALUACIÓN | G.1 Develop or adapt existing surveillance and monitoring framework with a set of recommended indicators (coverage, acceptability, disease surveillance etc…) for COVID-19 vaccine, including gathering information from facilities participating in vaccine delivery, and ensuring necessary human resource capacity is in place. Determine whether registration and reporting will be individual or aggregate, and to what extent existing tools and systems can be re-used | Yes | [22 empty] | 0 | Surveillance and monitoring framework developed/adapted.
| G.2 Develop or adapt necessary monitoring tools, including vaccination cards/certificates, facility-based nominal registers and/or tally sheets, vaccination reports, and analytical tools to monitor progress and coverage among different at-risk categories | [23 empty] | 0 | Necessary monitoring tools developed/adapted
| G.3 Develop or adapt necessary electronic monitoring tools including for medical records, immunization records, systems entry, and analytical tools that facilitate vaccine delivery and timely reporting | [23 empty] | 0 | Necessary electronic monitoring tools developed/adapted
| G.4 Ensure measures are in place for data protection, and appropriate data governance regulation is in place to monitor legitimate, appropriate and proportionate use and processing of data which may be routinely collected and managed in health information systems | [23 empty] | 0 | Data protection/governance regulation is in place
| G.5 Produce and distribute monitoring tools to eligible vaccination providers, develop, test and roll-out any changes to electronic systems, provide training for use of these tools and processes to traditional and new providers | [23 empty] | 0 | Monitoring tools produced and distributed, providers trained on use of these tools
| G.6 Ensure a mechanism with multiple intake points has been designed and is in place, and is operational for feedback and grievances in relation to the vaccine program | [23 empty] | 0 | Grievance/feedback mechanism is designed and in place
H. VACCINE, COLD CHAIN & LOGISTICS | H.1 Establish/strengthen the national logistics working group with appropriate terms of reference and standard operating procedures to coordinate COVID-19 vaccines and ancillary products deployment | Yes | [22 empty] | 0 | TOR and SOPs in place for national logistics working group
| H.2 Map key roles and responsibilities needed for vaccine and ancillary products deployment; collect and confirm contact information for key personnel and facilities | [23 empty] | 0 | Key roles and responsibilities mapped, contact information for key personnel collected
| H.3 Create a distribution strategy, including mapping the potential port(s) of entry, points of storage (stores) and stocking, and fallback facilities in the country with their respective cold chain storage (2-8C, -20C, -60/70C) and transportation capacity for vaccines and ancillary products, and ensure necessary human resource capacity is in place | [23 empty] | 0 | Distribution strategy (including mapping of key locations) created, covering vaccine transport and storage from import to point of delivery
| H.4 Assess dry storage and cold chain capacity and infrastructure needs at all levels with regards to the COVID-19 vaccines characteristics and fill the identified supply and logistics gaps | [23 empty] | 0 | Dry storage and cold chain assessed and gaps identified
| H.5 Identify implementing agencies and establish contractual agreements to prepare for vaccine introduction (e.g., vaccine warehousing, transport, waste management, cold chain capacity, etc) where applicable | [23 empty] | 0 | Implementing agency partners identified, contracts signed
| H.6 Provide COVID-appropriate standard operating procedures (SOPs), protocols, or guidelines for collection and disposal of medical waste to the relevant stakeholders | [23 empty] | 0 | SOPs for medical waste developed and distributed
| H.7 Update and implement systems and protocols for tracking and monitoring the stock management and distribution of vaccines and key supplies through the Government's existing Vaccine Logistics Management and Information System (VLMIS), including operating procedures to reflect the characteristics of COVID-19 vaccines (i.e. vial size, VVM,...) | [23 empty] | 0 | Systems/protocols for stock management and distribution of vaccines and supplies developed, updated, and implemented
| H.8 Establish security arrangements to ensure the integrity of COVID-19 vaccines and ancillary products throughout the supply chain | [23 empty] | 0 | Security arrangements in place for supply chain of vaccines and ancillary products
| H.9 Disseminate delivery and acceptance protocols, ensure monitoring arrangements are in place, and identify supervisory focal points at each facility | [23 empty] | 0 | Protocols for delivery and acceptance developed, distributed, and in place
I. VIGILANCIA DE LA SEGURIDAD | I.1 Ensure that guidelines, documented procedures and tools for planning and conducting vaccine pharmacovigilance activities (i.e. AEFI reporting, investigation, causality assessment, risk communication and response), have been developed and disseminated to surveillance facilities/sites | Yes | [22 empty] | 0 | Guidelines for pharmacovigilance developed and disseminated and roles defined at least up to the district level
| I.2 Ensure adequate and trained human resources are available to conduct surveillance of events attributable to vaccination | Yes | [22 empty] | 0 | Staff who are vaccinating and supervising vaccinators are trained in AEFI reporting
| I.3 Expedite appropriate representation, well defined ToRs and training the AEFI committee to review COVID-19 Vaccine safety data (e.g., causality assessment of serious AEFI, clusters of AEFI, emerging safety concerns etc.) | Yes | [22 empty] | 0 | Appropriate staffing, Tors developed and Training of national AEFI committee (and subnational AEFI committees if applicable) expedited and complete
| I.4 Identify provisions that require manufacturers to implement risk management plans and collect and report COVID-19 vaccine safety data to the NRA | Yes | [22 empty] | 0 | Provisions for manufacturer risk management identified and the RMP strategies discussed with the NRA and approved
| I.5 Plan active surveillance of specific COVID-19 vaccine related adverse events. If this is not possible, develop provisions that allow reliance on active surveillance data, decisions, and information from other countries or regional or international bodies | Yes | [22 empty] | 0 | Active surveillance of adverse events planned and country specific finalized and procedure documented
| I.6 Define roles and responsibilities and establish a coordination mechanism between relevant stakeholders (NRA, EPI, MAH, MOH, WHO and others) for exchange of COVID-19 Vaccine safety information | [23 empty] | 0 | Interagency coordination meeting organized, roles defined and coordination mechanism for safety information finalized and approved by MoH
| I.7 Identify and secure channels of data sharing mechanisms to share COVID-19 vaccine safety data and findings with relevant regional and international partners | [23 empty] | 0 | Identify and finalize mechanisms for sharing vaccine safety data and document the process after approval by stakeholders
| I.8 Establish compensation schemes in the event that there are unintended health consequences as result of vaccines, including no-fault liability funds, and ensure that associated policies are in place | [23 empty] | 0 | Compensation schemes in place
J. GENERACIÓN DE DEMANDA Y COMUNICACIÓN | J.1 Design and distribute a social mobilization and engagement strategy/demand plan (including advocacy, communications, social mobilization, risk and safety comms, community engagement, and training) to generate confidence, acceptance and demand for COVID-19 vaccines, including for engaging with national and local media, NGOs, social platforms, etc. Must include crisis communications preparedness planning | Yes | [22 empty] | 0 | Social mobilization and engagement strategy/demand plan is designed and distributed
| J.2 Establish data collection systems, including 1) social media listening and rumor management, and 2) assessing behavioral and social data | [23 empty] | 0 | Data collection systems are established
| J.3 Develop key messages and materials for public communications and advocacy, in alignment with demand plan | [23 empty] | 0 | Key messages and materials developed
K. INFRASTRUCTURE | K.1 Map and develop plan to provide for infrastructure needs, including for energy (primary and back-up power, especially in cold chain), communications (including connectivity) and water | [23 empty] | 0 | Infrastructure needs mapped, plan to meet needs developed

## Equivalency Table (hidden)
Assessment tools indicator equivalency table
VIRAF (Merged Tool) | VIRAT | VRAF (October) | VRAF Nov 4 | VIRAT/VIRAF, against VRAF Nov 4 |  |  |  | Weak / excess factor | Note for WB attention | Note for WHO attention
|  |  |  | Strong | Weak | Excess | Gap
Planning and Coordination
A.1 | A.1 | A1. 4 | A1.4 | x
A.2 | A.2 |  | A1.4 |  |  | x
A.3 | A.3 |  | A1.2 |  | x
A.4 | A.4 |  | A1.1 |  | x
A.5 |  | A.1.1 | [6 empty] | (addl. Requirement for A1.1)
A.6 | A.5 |  | A1.4 |  |  | x |  |  | (addl. Requirement for A1.1)
A.7 | A.6 |  | A1.1 | x
A.8 | A.7 | A.2.2, B.1.1, B.1.2 | B1.1 |  | x
A.9 |  | B.1.3 | B1.3 |  |  |  | x |  | OPCS-added |  | Move
A.10 | A.8 |  | B1.1 |  | x
Resources & Funding
B.1 | B.1 | A.4.1, A.4.2 | A4.1 |  | x
B.2 | B.2 | A.4.1, A.4.2 | A4.2 |  | x |  |  |  |  | VIRAF ignores VIRAT B.4??
B.3 | B.3 | A.4.1, A.4.2 | A4.1 |  | x
Regulatory
C.1 | C.1 |  | A2.1 | x
C.2 | C.2 | A.2.1 | A2.1 |  | x
C.3 | C.3 | A.2.3 | A2.3 |  | x
C.4 | C.4 |  | A2.3 |  | x
C.5 | C.5 |  | A2.1 |  | x
C.6 |  | A.2.8 |  |  |  |  | x |  | (
Prioritization, Targeting, & COVID-19 Surveillance
D.1 | D.1 |  | A1.3 |  | x
D.2 | D.2 | A.1.3 | A1.3 | x
D.3 | D.3 |  | A1.1 |  | x
Service Delivery
E.1 | E.1 | B.1.2 | B1.2 |  | x
E.2 |  | A.3.1 | A3.1 |  |  |  | x |  | important item but…
E.3 | E.2 | A.3.2, B.2.1 (create a strategy) | C2.1 | x
E.4 | E.3 | C.2.1 | C2.1 | x
E.5 |  | A.2.4 | A2.8 |  |  |  | x
E.6 | E.4 |  | A2.7 |  | x
E.7 |  | D.1.1 | D1.1 |  |  |  | x
E.8 |  | A.2.7 | A2.6 |  |  |  | x
E.9 |  |  | A2.7 |  | x |  |  |  | duplicative with E.6 |  | Merge E6 & E9
Training and Supervision
F.1 | F.1 | C.2.3 | C2.3 | x
F.2 | F.2 |  | C2.3 | x
F.3 |  | C.2.4 | C2.4 | x |  |  |  |  | dup w/G3
F.4 | F.3 |  | C2.3 | x
Monitoring & Evaluation
G.1 | G.1 | A.3.5 | C2.2 | x
G.2 | G.2 | C.2.2 | C2.2 | x
G.3 | G.2 | D.1.1 | C2.2 | x |  |  |  |  | D1.1…
G.4 |  | A.2.5 | A2.4 |  |  |  | x
G.5 | G.3 | D.1.1 | C2.4 | x |  |  |  |  | dup w/F3
G.6 |  | A.3.4 | A3.4 |  |  |  | x |  |  |  | integ…
Vaccine, Cold Chain, & Logistics
H.1 | H.1 |  | B2.1 | x
H.2 | H.2 |  | B2.1 | x
H.3 | H.3 | B.2.1 (detailed strategy) | B2.1 | x
H.4 | H.4 | B.2.2 | B2.2 | x
H.5 | H.5 | A.1.2 | B2.2 | x |  |  |  |  | A1.2 too generic
H.6 | H.6 | B.3.1, B.3.2, B.3.3 | B3.1 | x
H.7 | H.7 | B.2.3 | B2.3 | x
H.8 | H.8 | B.2.3 | B2.1 |  | x
H.9 |  | C.2.4 | C2.4 | x | [5 empty] | G.3 | Move to M&E
Surveillance
I.1 | I.1 | C.3.1 | C3.1 | x
I.2 | I.2 | C.3.1 | C3.1 | x
I.3 | I.3 | C.3.2 | C3.2 | x
I.4 | I.4 |  | C3.1 |  |  | x
I.5 | I.5 |  | C3.1 |  |  | x
I.6 | I.6 |  | C3.1 |  |  | x
I.7 | I.7 |  | C3.1 |  |  | x
I.8 |  | A.2.6, C.3.3 | A2.5, C3.3 |  |  |  | x
Demand Generation & Communication
J.1 | J.1 | C.1.1 | C1.1 | x
J.2 | J.2 | C.1.2 | C1.3 | x
J.3 | J.3 | C.1.3 | C1.2 | x
Infrastructure
K.1 |  | D.2.1, D.2.2 | D2.1, D2.2

## Conversion Nov 4 (hidden)
Select: | Region | Country | VIRAT Reporting Period
| AFR | Senegal | Oct-Nov |  |  |  | Calculated Status |  |  |  | Lookup tables |  |  | Pulldown menu lists |  |  |  |  | Extract selected country data
Selected:
World Bank VRAF (Nov 4) |  |  |  | Corresponding COVAX VIRAT Activities [Color coded for "strong," "weak," or "excess" predictors to VRAF Status - see footnote] | [15 empty] | Region | AFR
Core Activity Areas | Assessment Area | Indicators | Proxied from VIRAT | [5 empty] | VIRAT value | [10 empty] | Country | Senegal
[8 empty] | Type | Prim/Sec | Value | [9 empty] | 1 | 2 | 3 | 4
A. Planning and Management | A1. Vaccination objectives and targets | A1.1 Program objectives are defined and agreed by key stakeholders at central and sub-national levels, including representatives of target populations, community leaders, religious leaders, etc., and reflect the epidemiological situation and are adaptable to vaccine supply scenarios (protection of vulnerable populations, continuity of essential services, equity) | 2. In progress, early stage | A.6 Develop the National Deployment and Vaccination Plan (NDVP) with input from relevant bodies (National COVID-19 Response Coordinating Committee, CNCC, CTWG, NITAG, National Immunization Programme, National Regulatory Authority, AEFI committee and other relevant groups such as private sector). The NDVP should be in line with WHO guidance and SAGE recommendations (plan can be developed by adapting the Pandemic Influenza NDVP, if existing) | Not completed | develop_ndvp | 2 | A | 1 | 0 | Map VIRAT score to value |  |  | List of countries | Ctry# | List of Regions | List of Reporting Periods |  |  | Sep-20 (Pre-planning Baseline) | Oct-Nov 20 | Dic 20-ene 21 | Feb-mar 21
|  |  |  | A.4 Brief key ministries, NITAG, stakeholders and partners about COVID-19 vaccine introduction and their expected roles | In progress | nitag_briefed |  |  | 2 | 0.1 |  | Primary | Secondary | Senegal | 1 | AFR | Sep | 1 | ncc_established | 0 | Completed | 0 | 0
|  |  |  | D.3 Coordinate with national COVID-19 disease surveillance group to ensure relevant epidemiological data will be collected to inform planning of subsequent rounds of COVAX vaccination, including outbreak responses | Completed | coordinate_surv_group |  |  | 2 | 0.5 | Completed | 1 | 0.5 | Zambia | 5 |  | Oct-Nov | 2 | ntwg_established | 0 | Completed | 0 | 0
|  | A1.2 Implementing agencies (government or private) have been identified | 2. In progress, early stage | A.3 Establish or engage existing NTWG subcommittees, if required, to cover the following workstreams: 1) service delivery 2) vaccine, cold chain & logistics, 3) demand generation & communication (4) prioritization, targeting and COVID-19 surveillance, (5) Monitoring and Evaluation: determination and proof of eligibility, proof of vaccination, monitoring of coverage among at-risk groups, and monitoring of vaccine impact (6) Safety, including injury prevention and AEFI detection and response | Completed | ntwb_subcommittee | 2 | A | 2 | 0.5 | In Progress | 0.5 | 0.1 | Sao Tome & Principe | 9 | EAP | Dec-Jan | 3 | ntwb_subcommittee | 0 | Completed | 0 | 0
|  | A1.3 Priority target population(s) has been identified, enumerated and listed by location | 2. In progress, early stage | D.1 Monitor progress of NITAG working groups on COVID-19 vaccines and interim recommendations focusing on prioritization and risk groups | In progress | monitor_nitag_prg | 2 | A | 2 | 0.1 | Not Completed | 0 | 0 | Congo Democratic Republic | 13 | SAR | Feb-Mar | 4 | nitag_briefed | 0 | In progress | 0 | 0
|  |  |  | D.2 Estimate potential numbers of target populations that will be prioritized for access to vaccines stratified by target group and geographic location, i.e. prepare first to define, identify and estimate no. of HCWs | In progress | pop_priority |  |  | 1 | 0.5 | 0 | 0 | 0 | Seychelles | 17 | LCR |  |  | inform_SAGE | 0 | In progress | 0 | 0
|  | A1.4 Accountable body and leadership, such as EPI governance and management structure, exist and are functioning | 4. Completed | A.1 Establish (or engage an existing committee) a National Coordinating Committee (NCC) for COVID-19 vaccine introduction with terms of reference, roles and responsibilities and regular meetings | Completed | ncc_established | 4 | A | 1 | 1 |  |  |  | Cabo Verde | 21 | MNA |  |  | develop_ndvp | 0 | Not completed | 0 | 0
|  |  |  | A.2 Establish (or engage an existing working group) a National Technical Working Group (NTWG) for COVID-19 vaccine introduction with terms of reference, roles and responsibilities and regular meetings | Completed | ntwg_established |  |  | 3 | 0 | Map score to VRAF status |  |  | Liberia | 25 | ECA |  |  | identify_vaccineaccess | 0 | Completed | 0 | 0
|  |  |  | A.5 Inform regularly & disseminate global and regional guidance (i.e. SAGE) with NITAGs & RITAGs and support NITAG working groups on COVID-19 vaccines | In progress | inform_SAGE |  |  | 3 | 0 |  | Type A | Type B | Namibia | 29 |  |  |  | review_govtsign | 0 | In progress | 0 | 0
| A2. Regulation and Standards | A2.1 Appropriate regulatory measures are in place for approval of COVID-19 vaccines and related supplies | 4. Completed | C.1 Confirm to WHO the existence of any expedited regulatory pathway for approval of COVID-19 vaccines (i.e. emergency use authorization, exceptional approval/waiver mechanism based on reliance/recognition, abbreviated procedure, fast track, etc.). Time lines and maximum number of days should be mentioned. (expected timeline: maximum 15 working days) | Completed | existance_regpath | 4 | A | 1 | 1 | 1 | 1. Not Started | 1. 30% or less | Rwanda | 33 |  |  |  | estimate_finance | 0 | In progress | 0 | 0
|  |  |  | C.2 Ensure the national regulator or authority has clarified the requirements and documents needed for regulatory approvals of COVID-19 vaccines | Completed | clarified_req |  |  | 3 | 0 | 2 | 2. In progress, early stage | 2. 30-60% | Guinea | 37 |  |  |  | identify_fund_ICC | 0 | In progress | 0 | 0
|  |  |  | C.5 Ensure a system to waive local lot release testing based on review of summary protocols is in place. Identify the requirements and documents needed for NRA lot release or waiver of lot release for COVID-19 vaccines. Time lines and maximum number of days for lot release/waiver process should be mentioned. (expected timeline: maximum 2 days) | Completed | NRA_weiver |  |  | 3 | 0 | 3 | 3. In progress, maturity stage | 3. 60-90% | Benin | 41 |  |  |  | finalize_budgetmp | 0 | Not completed | 0 | 0
|  | A2.2 Regulatory measures are in place for procurement of COVID-19 vaccines and related supplies, including domestic and external procurement | [5 empty] | A |  |  | 4 | 4. Completed | 4. 90% or more | Cameroon | 45 |  |  |  | ensure_mechanisms | 0 | Not completed | 0 | 0
|  | A2.3 Regulatory measures are in place for import of COVID-19 vaccines and related supplies, including for taxes and tariffs | 2. In progress, early stage | C.3 Identify the requirements and documents needed to import COVID-19 vaccines | Completed | import_cvdvaccines | 2 | A | 2 | 0.5 |  |  |  | Chad | 49 |  |  |  | existance_regpath | 0 | Completed | 0 | 0
|  |  |  | C.4 Confirm to WHO the existence of an expedited import approval/waiver from appropriate authorities. Time lines and maximum number of days should be mentioned. (expected timeline: maximum 5 working days) | Completed | import_weiver |  |  | 3 | 0 |  |  |  | Cote d'Ivoire | 53 |  |  |  | clarified_req | 0 | Completed | 0 | 0
|  | A2.4 Regulatory measures are in place for data protection, and appropriate data governance regulation is in place to monitor legitimate, appropriate and proportionate use and processing of data which may be routinely collected and managed in health information systems | [5 empty] | A | [5 empty] | Nigeria | 57 |  |  |  | import_cvdvaccines | 0 | Completed | 0 | 0
|  | A.2.5. Regulatory capacity to accommodate requests for no-fault liability funds and any related regulatory requirements (if not already in existence) is in place | [5 empty] | A | [5 empty] | Sierra Leone | 61 |  |  |  | import_weiver | 0 | Completed | 0 | 0
|  | A.2.6 Regulatory measures regarding consent to vaccinations, process for agreeing to or refusing to be vaccinated, and measures to protect those that refuse to be vaccinated are in place | [5 empty] | A | [5 empty] | Niger | 65 |  |  |  | NRA_weiver | 0 | Completed | 0 | 0
|  | A.2.7 Regulatory measures are in place regarding personnel who will be carrying out vaccinations, including all staff/personnel/consultants etc. engaged in such activities (cover military personnel also, if possible), and include requirements relating to chemical, physical and biological substances, not engaging in sexual exploitation and abuse and sexual harassment, participation in training, reporting and non-retaliation | 2. In progress, early stage | E.4 Ensure availability of plans to safeguard the security of staff (e.g. during an emergency or major campaign) as well as security at the central and/or regional storage facilities and for in-transit of products | Completed | availplans_staffsecurity | 2 | A | 2 | 0.5 |  |  |  | Angola | 69 |  |  |  | monitor_nitag_prg | 0 | In progress | 0 | 0
|  | A2.8 For delivery through private facilities: Standard Operating Procedures are developed, including a complaints-handling mechanism; mechanisms for certification of facilities, of financing and of monitoring of performance and integrity checks are developed and approved; and service quality and performance and reporting standards are agreed | [5 empty] | A | [5 empty] | Burkina Faso | 73 |  |  |  | pop_priority | 0 | In progress | 0 | 0
| A3. Performance management and M&E | A3.1 A gap analysis of delivery and storage capacity has been conducted, and potential bottlenecks, capacity deficiencies and recommendations for improvement have been identified | [5 empty] | A | [5 empty] | Guinea-Bissau | 77 |  |  |  | coordinate_surv_group | 0 | Completed | 0 | 0
|  | A3.2 Outreach for target populations has been scheduled, necessary planning for locations and logistics has been carried out, and an information awareness program has been designed and is being implemented | [5 empty] | A | [5 empty] | South Sudan | 81 |  |  |  | update_protocols_ipc | 0 | Completed | 0 | 0
|  | A.3.4 A mechanism with multiple intake points has been designed and is in place, and is operational for feedback and grievances in relation to the vaccine program | [5 empty] | A | [5 empty] | Kenya | 85 |  |  |  | potentials_del_strategy | 0 | In progress | 0 | 0
|  | A3.5 A monitoring & evaluation (M&E) framework for program roll-out has been developed, including for gathering information from facilities participating in vaccine delivery, and the necessary human resource capacity is in place | [5 empty] | A | [5 empty] | Uganda | 89 |  |  |  | masterlist_ServProviders | 0 | In progress | 0 | 0
| A4. Budgeting | A4.1 COVID vaccine program costs (vaccine, operating costs, HR and capital costs) have been included in government budgetary and/or planning documents approved by the appropriate authority; in addition, appropriation or allocation (from MOF/treasury) is included in the cash planning as an additional means to ensure that financing is indeed readily available | 2. In progress, early stage | B.1 Estimate financial and human resources needed (including surge capacity requirements) to conduct the deployment and vaccination operations in the designated points and in the required number of days | In progress | estimate_finance | 2 | A | 2 | 0.1 |  |  |  | Swaziland | 93 |  |  |  | availplans_staffsecurity | 0 | Completed | 0 | 0
|  |  |  | B.3 Finalize the budgeted micro-plans for vaccination including plans for other relevant components such as demand generation, risk communications and safety surveillance | Not completed | finalize_budgetmp |  |  | 2 | 0 |  |  |  | Eritrea | 97 |  |  |  | trainplan_covid | 0 | In progress | 0 | 0
|  | A.4.2 Management aspects of appropriations from the MOF/Treasury are in place | 2. In progress, early stage | B.2 Identify funding mechanisms in collaboration with relevant stakeholders including Inter-Agency Coordinating Committee (ICC), if available at country | In progress | identify_fund_ICC | 2 | A | 2 | 0.1 |  |  |  | Madagascar | 101 |  |  |  | adapt_trainmat | 0 | Not completed | 0 | 0
|  |  |  | B.4 Ensure mechanism to release and distribute funds to lowest levels for operations | Not completed | ensure_mechanisms |  |  | 2 | 0 |  |  |  | Gambia | 105 |  |  |  | virtual_phys_train | 0 | Not completed | 0 | 0
B. Supply and Distribution | B1. Vaccines, PPEs and other medical and non-medical supplies | B1.1 A procurement plan, including costs of items, due diligence mechanisms and purchasing strategies for COVID-19 vaccine(s) and ancillary supplies (syringes, safety boxes), has been developed; budget has been approved; and monitoring arrangements are agreed and updated as needed [if COVID-19 vaccines procurement arrangements have been made or are under discussion, e.g. bilateral purchase arrangements or Advance Purchase Commitments, please mention it here] | 2. In progress, early stage | A.7 Identify and plan for the national vaccine access/procurement approach (e.g. COVAX Facility, bilateral purchase agreement, procurement through UN agency, self-procurement) and complete required paperwork. (Additional information to follow) | Completed | identify_vaccineaccess | 2 | A | 2 | 0.5 |  |  |  | Ghana | 109 |  |  |  | adapt_mef | 0 | In progress | 0 | 0
|  |  |  | A.8 Review and prepare Government signature for legal agreement to receive Covid-19 vaccine (Additional information to follow) | In progress | review_govtsign |  |  | 2 | 0.1 |  |  |  | Ethiopia | 113 |  |  |  | adapt_mon_tools | 0 | In progress | 0 | 0
|  | B1.2 Personal Protective Equipment and IPC equipment needs have been identified for individuals supporting the immunization program, and a procurement plan, including costs of items, and due diligence arrangements have been developed | 2. In progress, early stage | E.1 Update protocols for infection prevention and control measures including adequate personal protection equipment (PPE) to minimize exposure risk during immunization sessions | Completed | update_protocols_ipc | 2 | A | 2 | 0.5 |  |  |  | Malawi | 117 |  |  |  | mon_tools_prod | 0 | Not completed | 0 | 0
|  | B1.3 Waste management equipment and supplies has been procured for appropriate implementation of protocols | [5 empty] | A | [5 empty] | Congo Republic | 121 |  |  |  | strengthen_NWLG | 0 | Completed | 0 | 0
| B2. Logistics and cold chain | B2.1 A distribution strategy, from points-of-entry to the front-line, including transport, stocking and other components of the supply chain has been developed and operationalized, and the necessary human resource capacity is in place | 4. Completed | H.1 Establish/strengthen the national logistics working group with appropriate terms of reference and standard operating procedures to coordinate COVID-19 vaccines and ancillary products deployment | Completed | strengthen_NWLG | 4 | A | 1 | 1 |  |  |  | Mozambique | 125 |  |  |  | map_roles | 0 | Completed | 0 | 0
|  |  |  | H.2 Map key roles and responsibilities needed for vaccine and ancillary products deployment; collect and confirm contact information for key personnel and facilities | Completed | map_roles |  |  | 1 | 1 |  |  |  | Zimbabwe | 129 |  |  |  | map_entrypoints | 0 | Completed | 0 | 0
|  |  |  | H.3 Map the potential port(s) of entry, points of storage (stores), and fallback facilities in the country with their respective cold chain storage (2-8C, -20C, -60/70C) and transportation capacity for vaccines and ancillary products | Completed | map_entrypoints |  |  | 1 | 1 |  |  |  | Gabon | 133 |  |  |  | assess_dry_coldchain | 0 | In progress | 0 | 0
|  |  |  | H.8 Establish security arrangements to ensure the integrity of COVID-19 vaccines and ancillary products throughout the supply chain | Not completed | ensure_integrity |  |  | 3 | 0 | [8 empty] | vaccine_agreements | 0 | Completed | 0 | 0
|  | B2.2 Cold chain equipment and cold storage infrastructure at participating locations is in place, and if not, the needs have been identified and a procurement plan / purchasing strategy for procurement of extra infrastructure is in place or is under discussion | 3. 60-90% | H.4 Assess dry storage and cold chain capacity at all levels with regards to the COVID-19 vaccines characteristics and fill the identified supply and logistics gaps | In progress | assess_dry_coldchain | 3 | B | 1 | 0.5 | [8 empty] | provide_SOP | 0 | Not completed | 0 | 0
|  |  |  | H.5 Establish contractual agreements to prepare for vaccine introduction (e.g., vaccine warehousing, transport, waste management, cold chain capacity, etc) where applicable | Completed | vaccine_agreements |  |  | 1 | 1 | [8 empty] | update_VVM | 0 | Not completed | 0 | 0
|  | B2.3 Systems and protocols for tracking and monitoring the distribution of vaccines and key supplies are in place through the Government's existing Vaccine Logistics Management and Information System (VLMIS) | 1. Not Started | H.7 Update vaccine stock management tools and operating procedures to reflect the characteristics of COVID-19 vaccines (i.e. vial size, VVM,...) | Not completed | update_VVM | 1 | A | 1 | 0 | [8 empty] | ensure_integrity | 0 | Not completed | 0 | 0
| B3. Waste management | B3.1 Waste Management protocols appropriate for COVID-19, both hazardous and non-hazardous, and including practices and guidelines on disposal routes have been developed and disseminated | 1. Not Started | H.6 Provide standard operating procedures (SOPs) or guidelines for collection and disposal of medical waste to the relevant stakeholders | Not completed | provide_SOP | 1 | A | 1 | 0 | [8 empty] | pharmacovigilance | 0 | Completed | 0 | 0
|  | B3.2 Appropriate waste management systems are in place in all relevant sites, and adequate trained human resource capacity is available | [5 empty] | B | [10 empty] | assure_vigilance | 0 | Completed | 0 | 0
|  | B3.3 Properly-licensed waste management providers (especially for hazardous waste storage, transportation and disposal) are identified and can be operationalized | [5 empty] | A | [10 empty] | train_AEFI | 0 | Completed | 0 | 0
C. Program Delivery | C1. Community engagement and advocacy | C1.1 Social mobilization, engagement strategy and information awareness program have been designed and developed to generate vaccine acceptance, confidence and demand, including for engaging with national and local media, NGOs, social platforms, etc., and human resources for community outreach and risk management that also explains how complaints may be lodged and how they will be resolved, are available at all levels | 2. In progress, early stage | J.1 Design a demand plan (includes advocacy, communications, social mobilization, risk and safety comms, community engagement, and training) to generate confidence, acceptance and demand for COVID-19 vaccines. Must include a crisis communications preparedness planning | In progress | design_demandplan | 2 | A | 1 | 0.5 | [8 empty] | impl_riskmgmtplans | 0 | Completed | 0 | 0
|  | C1.2 Social and mobilization strategy and risk communication materials have been disseminated to relevant stakeholders at subnational levels | 1. Not Started | J.3 Develop key messages and materials for public communications and advocacy, in alignment with demand plan | Not completed | develop_keys | 1 | A | 1 | 0 | [8 empty] | plan_activesurv | 0 | Completed | 0 | 0
|  | C1.3 Data collection systems have been established for (i) social media listening and rumor management; and (ii) assessing behavioral and social data | 1. Not Started | J.2 Establish data collection systems, including 1) social media listening and rumor management, and 2) assessing behavioral and social data | Not completed | establish_dat_C | 1 | A | 1 | 0 | [8 empty] | NRA_mgt | 0 | Completed | 0 | 0
| C2. Points of delivery | C2.1 Points of delivery, including static and outreach (e.g., health facilities, community centers, house-to-house) and associated medical supplies have been mapped to target population areas | 2. In progress, early stage | E.2 Identify potential COVID-19 vaccine delivery strategies leveraging both existing vaccination platforms and non-vaccination delivery approaches to best reach identified target groups | In progress | potentials_del_strategy | 2 | A | 1 | 0.5 | [8 empty] | comms_channel | 0 | Completed | 0 | 0
|  |  |  | E.3 Identify and develop a master list and strategy of service providers who could effectively deliver COVID-19 vaccine to various target populations | In progress | masterlist_ServProviders |  |  | 1 | 0.5 | [8 empty] | design_demandplan | 0 | In progress | 0 | 0
|  | C2.2 Monitoring tools such as vaccination cards/certificates, facility-based nominal registers and/or tally sheets, vaccination reports (paper and/or electronic) and analytical tools to monitor progress and coverage among different at-risk categories have been developed | 2. In progress, early stage | G.1 Develop or adapt existing surveillance and monitoring framework with a set of recommended indicators (coverage, acceptability, disease surveillance etc…) for COVID-19 vaccine. Determine whether registration and reporting will be individual or aggregate, and to what extent existing tools and systems can be re-used | In progress | adapt_mef | 2 | A | 1 | 0.5 | [8 empty] | establish_dat_C | 0 | Not completed | 0 | 0
|  |  |  | G.2 Develop or adapt necessary monitoring tools or adapt existing tools: vaccination card/certificate - facility-based nominal registers and/or tally sheets, vaccination reports (paper and/or electronic) and analytical tools to monitor progress and coverage among different at-risk categories | In progress | adapt_mon_tools |  |  | 1 | 0.5 | [8 empty] | develop_keys | 0 | Not completed | 0 | 0
|  | C2.3 Adequate and trained human resources, including for safe injection practices, are available in all participating facilities | 2. 30-60% | F.1 Develop a training plan to prepare for COVID-19 vaccine introduction that includes key groups of participants, content topic areas, key training partners and training methods (in-person or virtual). WHO will provide a template for guidance | In progress | trainplan_covid | 2 | B | 1 | 0.5
|  |  |  | F.2 Adapt and translate training materials developed by WHO and develop additional training materials as outlined in the training plan | Not completed | adapt_trainmat |  |  | 1 | 0
|  |  |  | F.3 Conduct virtual and/or in person trainings as outlined in the training plan | Not completed | virtual_phys_train |  |  | 1 | 0
|  | C2.4 Delivery and acceptance protocols have been disseminated, monitoring arrangements are in place, and supervisory focal points at each facility have been identified | 1. Not Started | G.3 Produce and distribute monitoring tools to eligible vaccination providers, develop, test and roll-out any changes to electronic systems, provide training for use of these tools and processes to traditional and new providers | Not completed | mon_tools_prod | 1 | A | 1 | 0
| C3. Vaccine safety surveillance | C3.1 Protocols for adapting surveillance systems for Vaccine Preventable Diseases and AEFI to conduct surveillance of events attributable to vaccination have been developed and disseminated to surveillance facilities/sites and adequate and trained human resources are available to conduct surveillance of events attributable to vaccination | 4. Completed | I.1 Ensure that guidelines, documented procedures and tools for planning and conducting vaccine pharmacovigilance activities (i.e. AEFI reporting, investigation, causality assessment, risk communication and response) are available | Completed | pharmacovigilance | 4 | A | 1 | 1
|  |  |  | I.2 Assure competent and trained staff to perform vigilance activities | Completed | assure_vigilance |  |  | 1 | 1
|  |  |  | I.4 Identify provisions that require manufacturers to implement risk management plans and collect and report COVID-19 vaccine safety data to the NRA | Completed | impl_riskmgmtplans |  |  | 3 | 0
|  |  |  | I.5 Plan active surveillance of specific COVID-19 vaccine related adverse events. If this is not possible, develop provisions that allow reliance on active surveillance data, decisions, and information from other countries or regional or international bodies | Completed | plan_activesurv |  |  | 3 | 0
|  |  |  | I.6 Establish a coordination mechanism between relevant stakeholders (NRA, EPI, MAH, MOH, WHO and others) for exchange of COVID-19 Vaccine safety information | Completed | NRA_mgt |  |  | 3 | 0
|  |  |  | I.7 Secure communication channels to share COVID-19 vaccine safety data and findings with relevant regional and international partners | Completed | comms_channel |  |  | 3 | 0
|  | C3.2 AEFI committees have been trained to review COVID-19 Vaccine safety data (e.g., causality assessment of serious AEFI, clusters of AEFI, emerging safety concerns etc.) | 4. Completed | I.3 Expedite training the AEFI committee to review COVID-19 Vaccine safety data (e.g., causality assessment of serious AEFI, clusters of AEFI, emerging safety concerns etc.) | Completed | train_AEFI | 4 | A | 1 | 1
|  | C.3.3 Compensation schemes in the event that there are unintended health consequences as result of vaccines have been established | [5 empty] | A
D. Supporting Systems and Infrastructure | D1. Data quality | D1.1 Appropriate institutional and electronic management systems (medical records, systems entry, immunization cards) that facilitate successful delivery of vaccines are in place to allow timely and accurate reporting on delivery, and adequate and trained human resources are available | [5 empty] | B
| D2. Infrastructure | D2.1 Inputs related to infrastructure for energy (primary and back-up power) and water are in place | [5 empty] | B
|  | D.2.2. Appropriate IT Infrastructure, including communications and internet connectivty, is in place | [5 empty] | B
* | "Strong" VIRAT activity is considered equivalent to VRAF indicator in terms of its scope of readiness assessment (if VIRAT activity "completed", VRAF status also "completed").
"In progress" status of "strong" VIRAT activity is conservatively iterpreted as VRAF's "early stage" status.
If more than one strong VIRAT activities correspond to one VRAF indicator, status of all the VIRAT activities need to be "completed" for the corresponding VRAF indicator status to be "completed."
"Weak" VIRAT activity is considered partially, but not fully, equivalent to VRAF indicator in terms of its scope of readiness assessment (even if VRAT "completed", VRAF still "in progress" - conservatively, at an early stage).
VIRAT activity neither "strong" or "weak" (i.e. "excess") assesses what is relevant to, but beyond the scope of, VRAF indicator and does not affect our assessment of VRAF indicator status.

## Index (hidden)
Version as of November 11, 2020
Introduction
This workbook is meant to help implement VRAF (Vaccine Readiness Assessment Framework) in countries where WHO's VIRAT is being deployed,
by estimating VRAF indicators' status using relevant VIRAT assessment findings as proxies. | (Source: WHO Africa VIRAT dashboard)
- VIRAT includes 48 activities, with binary status (3 levels of readiness) snapshots over time, actions planned (by when and by whom), with some costing.
- VRAF has 40 indicators, with binary status (4 levels of readiness), needs and gaps in terms of admin actions, materials, human resources and financing.
With the limitations of VIRAT data currently available, this tool only uses binary status part of VIRAT to estimate binary status of VRAF indicators.
Approach
Status of 48 activities in VIRAT collectively inform status of 24, out of the 40, indicators in VRAF.
Given the differences in these assessments, VIRAT findings are used to estimate relevant VRAF indicator status, following a decision-tree approach:
Countries covered
WHO and partners have shared with us the October-November snapshot status of VIRAT activities in 21 countries.
|  | Group 1: | Group 2:
VIRAT activities are covered differently among three groups of the countries assessed: |  | Senegal | Nigeria
- Group 1 countries have all of the 48 VIRAT activities assessed. |  | Zambia | Sierra Leone
For these countries, the worksheet estimate VIRAF indicators status using all information available. |  | Sao Tome & Principe | Niger
|  | Congo Democratic Republic | Angola
- Group 2 countries vary in coverage of the 48 activities (from 38 in Nigeria to 6 in South Sudan). |  | Seychelles | Burkina Faso
For these countries, the worksheet assumes that the activities not assessed have no progress. |  | Cabo Verde | Guinea-Bissau
|  | Liberia | South Sudan
- Group 3 countries have more than one (including contradictory) status reports per VIRAT activity. |  | Namibia | Group 3:
From the contradictory reports in these countries, the worksheet chooses the higher progress status. |  | Rwanda | Cameroon
|  | Guinea | Chad
|  | Benin | Cote d'Ivoire
Overview sheet of the workbook presents estimated VRAF indicators status for all countries covered by VIRAT so far.
The workbook contains one sheet per country with estimated VRAF indicators status.
Conversion sheet of the workbook provides detailed mapping between VIRAT findings and VRAF indicators, including the missing ones, by country.
Guidance
This estimation is meant to inform and ease, but not replace, the data gathering ongoing or planned by the teams to implement VRAF.
The teams' and client's judgments, considering ountry-specific circumstances, should override the VIRAT-informed estimation.
Vaccine delivery taskforce will continue to update this workbook upon additional information on VIRAT findings.
For questions or comments on this workbook, please contact: Naoto Kanehira (nkanehira@worldbank.org) and Micaela Mussini (mmussini@worldbank.org).

## VRAF Nov 4 (hidden)
Covid-19 Vaccine Readiness Assessment Framework
Core Activity Areas | Assessment Area | Indicators | Status (keep only one of the following) | Administrative, organizational, legislative/regulatory and coordination requirements |  | Medical supplies and supporting infrastructure equipment and transport |  | Human resources and training |  | Financing
|  |  |  | Central | Sub-National (Departments, Regions, Districts)
|  |  |  | What actions need to be undertaken to get to 'completed' or 'more than 90%' status | What actions need to be undertaken to get to 'completed' or 'more than 90%' status | What medical supplies and equipment are needed to get to 'completed' or 'more than 90%' status | What would it cost to procure the medical supplies and equipment to get to 'completed' or 'more than 90%' status | What are the staffing and training requirements to get a 'completed' or 'more than 90%' status | What would it cost to hire and train staff needed to get to 'completed' or 'more than 90%' status | What is the total financing needed to procure the medical supplies & equipment, and hire & train staff (and admin costs, if any), to get to a 'completed' or 'more than 90%' status
[7 empty] | X1 |  | X2 | X1+X2+admin costs if any
A. Planning and Management | A1. Vaccination objectives and targets | A1.1 Program objectives are defined and agreed by key stakeholders at central and sub-national levels, including representatives of target populations, community leaders, religious leaders, etc., and reflect the epidemiological situation and are adaptable to vaccine supply scenarios (protection of vulnerable populations, continuity of essential services, equity) | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A1.2 Implementing agencies (government or private) have been identified | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A1.3 Priority target population(s) has been identified, enumerated and listed by location | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A1.4 Accountable body and leadership, such as EPI governance and management structure, exist and are functioning | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
| A2. Regulation and Standards | A2.1 Appropriate regulatory measures are in place for approval of COVID-19 vaccines and related supplies | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A2.2 Regulatory measures are in place for procurement of COVID-19 vaccines and related supplies, including domestic and external procurement | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A2.3 Regulatory measures are in place for import of COVID-19 vaccines and related supplies, including for taxes and tariffs | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A2.4 Regulatory measures are in place for data protection, and appropriate data governance regulation is in place to monitor legitimate, appropriate and proportionate use and processing of data which may be routinely collected and managed in health information systems | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A.2.5. Regulatory capacity to accommodate requests for no-fault liability funds and any related regulatory requirements (if not already in existence) is in place | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A.2.6 Regulatory measures regarding consent to vaccinations, process for agreeing to or refusing to be vaccinated, and measures to protect those that refuse to be vaccinated are in place | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A.2.7 Regulatory measures are in place regarding personnel who will be carrying out vaccinations, including all staff/personnel/consultants etc. engaged in such activities (cover military personnel also, if possible), and include requirements relating to chemical, physical and biological substances, not engaging in sexual exploitation and abuse and sexual harassment, participation in training, reporting and non-retaliation | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A2.8 For delivery through private facilities: Standard Operating Procedures are developed, including a complaints-handling mechanism; mechanisms for certification of facilities, of financing and of monitoring of performance and integrity checks are developed and approved; and service quality and performance and reporting standards are agreed | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
| A3. Performance management and M&E | A3.1 A gap analysis of delivery and storage capacity has been conducted, and potential bottlenecks, capacity deficiencies and recommendations for improvement have been identified | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A3.2 Outreach for target populations has been scheduled, necessary planning for locations and logistics has been carried out, and an information awareness program has been designed and is being implemented | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A.3.4 A mechanism with multiple intake points has been designed and is in place, and is operational for feedback and grievances in relation to the vaccine program | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A3.5 A monitoring & evaluation (M&E) framework for program roll-out has been developed, including for gathering information from facilities participating in vaccine delivery, and the necessary human resource capacity is in place | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
| A4. Budgeting | A4.1 COVID vaccine program costs (vaccine, operating costs, HR and capital costs) have been included in government budgetary and/or planning documents approved by the appropriate authority; in addition, appropriation or allocation (from MOF/treasury) is included in the cash planning as an additional means to ensure that financing is indeed readily available | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A.4.2 Management aspects of appropriations from the MOF/Treasury are in place | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
B. Supply and Distribution | B1. Vaccines, PPEs and other medical and non-medical supplies | B1.1 A procurement plan, including costs of items, due diligence mechanisms and purchasing strategies for COVID-19 vaccine(s) and ancillary supplies (syringes, safety boxes), has been developed; budget has been approved; and monitoring arrangements are agreed and updated as needed [if COVID-19 vaccines procurement arrangements have been made or are under discussion, e.g. bilateral purchase arrangements or Advance Purchase Commitments, please mention it here] | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed |  |  | Vaccine (doses) Syringes & safety boxes Other items: alcohol wipes, plasters, cotton swabs, etc.
|  | B1.2 Personal Protective Equipment and IPC equipment needs have been identified for individuals supporting the immunization program, and a procurement plan, including costs of items, and due diligence arrangements have been developed | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed |  |  | PPEs for health care workers: 1. Masks 2. Gowns 3. Face Shields 4. Gloves 5. Boots 6. Sanitizer 7.Handwashing Stations
|  | B1.3 Waste management equipment and supplies has been procured for appropriate implementation of protocols | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
| B2. Logistics and cold chain | B2.1 A distribution strategy, from points-of-entry to the front-line, including transport, stocking and other components of the supply chain has been developed and operationalized, and the necessary human resource capacity is in place | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | B2.2 Cold chain equipment and cold storage infrastructure at participating locations is in place, and if not, the needs have been identified and a procurement plan / purchasing strategy for procurement of extra infrastructure is in place or is under discussion | 1. 30% or less; 2. 30-60%; 3. 60-90%; 4. 90% or more |  |  | Refrigerated vehicles Refrigerated Storage Temperature monitoring devices, etc.
|  | B2.3 Systems and protocols for tracking and monitoring the distribution of vaccines and key supplies are in place through the Government's existing Vaccine Logistics Management and Information System (VLMIS) | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
| B3. Waste management | B3.1 Waste Management protocols appropriate for COVID-19, both hazardous and non-hazardous, and including practices and guidelines on disposal routes have been developed and disseminated | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | B3.2 Appropriate waste management systems are in place in all relevant sites, and adequate trained human resource capacity is available | 1. 30% or less; 2. 30-60%; 3. 60-90%; 4. 90% or more
|  | B3.3 Properly-licensed waste management providers (especially for hazardous waste storage, transportation and disposal) are identified and can be operationalized | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
C. Program Delivery | C1. Community engagement and advocacy | C1.1 Social mobilization, engagement strategy and information awareness program have been designed and developed to generate vaccine acceptance, confidence and demand, including for engaging with national and local media, NGOs, social platforms, etc., and human resources for community outreach and risk management that also explains how complaints may be lodged and how they will be resolved, are available at all levels | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | C1.2 Social and mobilization strategy and risk communication materials have been disseminated to relevant stakeholders at subnational levels | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | C1.3 Data collection systems have been established for (i) social media listening and rumor management; and (ii) assessing behavioral and social data | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
| C2. Points of delivery | C2.1 Points of delivery, including static and outreach (e.g., health facilities, community centers, house-to-house) and associated medical supplies have been mapped to target population areas | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | C2.2 Monitoring tools such as vaccination cards/certificates, facility-based nominal registers and/or tally sheets, vaccination reports (paper and/or electronic) and analytical tools to monitor progress and coverage among different at-risk categories have been developed | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | C2.3 Adequate and trained human resources, including for safe injection practices, are available in all participating facilities | 1. 30% or less; 2. 30-60%; 3. 60-90%; 4. 90% or more |  |  |  |  | Training Per diem Hazard pay for health care workers
|  | C2.4 Delivery and acceptance protocols have been disseminated, monitoring arrangements are in place, and supervisory focal points at each facility have been identified | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
| C3. Vaccine safety surveillance | C3.1 Protocols for adapting surveillance systems for Vaccine Preventable Diseases and AEFI to conduct surveillance of events attributable to vaccination have been developed and disseminated to surveillance facilities/sites and adequate and trained human resources are available to conduct surveillance of events attributable to vaccination | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | C3.2 AEFI committees have been trained to review COVID-19 Vaccine safety data (e.g., causality assessment of serious AEFI, clusters of AEFI, emerging safety concerns etc.) | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed |  |  |  |  | Adverse event from immunization (AEFI) surveillance Training Per diem
|  | C.3.3 Compensation schemes in the event that there are unintended health consequences as result of vaccines have been established | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
D. Supporting Systems and Infrastructure | D1. Data quality | D1.1 Appropriate institutional and electronic management systems (medical records, systems entry, immunization cards) that facilitate successful delivery of vaccines are in place to allow timely and accurate reporting on delivery, and adequate and trained human resources are available | 1. 30% or less; 2. 30-60%; 3. 60-90%; 4. 90% or more | Vaccine Logistics Management and Information System; Vaccination Certificates
| D2. Infrastructure | D2.1 Inputs related to infrastructure for energy (primary and back-up power) and water are in place | 1. 30% or less; 2. 30-60%; 3. 60-90%; 4. 90% or more |  |  | Generators Water Supply
|  | D.2.2. Appropriate IT Infrastructure, including communications and internet connectivty, is in place | 1. 30% or less; 2. 30-60%; 3. 60-90%; 4. 90% or more |  |  | Telecom IT Infrastructure – Computers, Cellphones etc.

## VRAF Oct (hidden)
Covid-19 Vaccine Readiness Assessment Framework
Core Activity Areas | Assessment Area | Indicators | Status (keep only one of the following) | Administrative, organizational, legislative/regulatory and coordination requirements | [5 empty] | Medical supplies and supporting infrastructure equipment and transport |  |  |  | Human resources and training |  |  |  | Financing
|  |  |  | Central |  |  | Sub-National: Departments, Regions, Districts
|  |  |  | Brief assessment of current status | What administrative, organizational, regulatory and coordination actions need to be undertaken to get to 'completed' or 'more than 90%' status | What would it cost to undertake the administrative, organizational, regulatory and coordination actions to get to 'completed' or 'more than 90%' status | Brief assessment of current status | What administrative, organizational, regulatory and coordination actions need to be undertaken to get to 'completed' or 'more than 90%' status | What would it cost to undertake the administrative, organizational, regulatory and coordination actions to get to 'completed' or 'more than 90%' status | What medical supplies and equipment are needed to get to 'completed' of 'more than 90%' status | What is currently available | What medical supplies and equipment need to be procured to meet the shortfall | What would it cost to procure the medical supplies and equipment to get to 'completed' or 'more than 90%' status | What are the staffing and training requirements to get a 'completed' or 'more than 90%' status | What is currently available | What staff needs to be hired and trained to meet the shortfall | What would it cost to hire and train staff needed to get to 'completed' or 'more than 90%' status | What is the total financing needed to undertake the administrative actions, procure the medical supplies and equipment, and hire and train staff to get to a 'completed' or 'more than 90%' status
[6 empty] | X1 |  |  | X2 |  |  |  | X3 |  |  |  | X4 | X1+X2+X3+X4
A. Planning and Management | A1. Vaccination objectives and targets | A1.1 Program objectives are defined and agreed to by key stakeholders at the central and sub-national levels, and reflect the epidemiological situation and are adaptable to vaccine supply scenarios (protection of vulnerable populations, continuity of essential services, equity) | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A1.2 Implementing agencies (government or private) have been identified | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A1.3 Priority target population(s) has been identified, enumerated and listed by location | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A1.4 Accountable body and leadership, such as EPI governance and management structure, exist and are functioning | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
| A2. Regulation and Standards | A2.1 Regulatory measures are in place for approval of COVID-19 vaccines and related supplies | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A2.2 Regulatory measures are in place for procurement of COVID-19 vaccines and related supplies, including domestic and external procurement | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A2.3 Regulatory measures are in place for import of COVID-19 vaccines and related supplies, including for taxes and tariffs | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A2.4 For delivery through private facilities: Standard Operating Procedures are developed, a mechanism for certification of facilities is approved, a financing mechanism is developed and a mechanism for monitoring of performance and service quality is agreed | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
| A3. Performance management and M&E | A3.1 A gap analysis of delivery capacity has been conducted, and potential bottlenecks, capacity deficiencies and recommendations for improvement have been identified | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A3.2 Outreach for target populations has been scheduled and necessary planning for locations and logistics has been carried out | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A3.3 A monitoring & evaluation (M&E) framework for program roll-out has been developed, including for gathering information from facilities participating in vaccine delivery, and the necessary human resource capacity is in place | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
| A4. Budgeting | A1.4 COVID vaccine program costs (vaccine, operating costs, HR and capital costs) have been included in government budgetary and/or planning documents approved by the appropriate authority | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
B. Supply and Distribution | B1. Vaccines, PPEs and other supplies | B1.1 A procurement plan and purchasing strategy for a COVID-19 vaccine(s) and ancillary supplies (syringes, safety boxes) has been developed | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed | [6 empty] | Vaccine (doses) Syringes & safety boxes
|  | B1.2 Personal Protective Equipment needs have been identified for individuals supporting the immunization program, and a procurement plan has been developed | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed | [6 empty] | PPEs for health care workers: 1. Masks 2. Gowns 3. Face Shields 4. Gloves 5. Boots 6. Sanitizer
| B2. Logistics and cold chain | B2.1 A distribution strategy, from points-of-entry to the front-line, including transport, stocking and other components of the supply chain has been developed and operationalized, and the necessary human resource capacity is in place | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | B2.2 Requirement of cold chain equipment and cold storage infrastructure at participating locations has been determined and procurement sources identified | 1. 30% or less; 2. 30-60%; 3. 60-90%; 4. 90% or more
|  | B2.3 Systems and protocols for tracking and monitoring the distribution of vaccines and key supplies are in place through the Government's existing Vaccine Logistics Management and Information System (VLMIS) | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
C. Program Delivery | C1. Community engagement and advocacy | C1.1 A social mobilization and engagement strategy has been developed to generate vaccine confidence and demand, including for engaging with national and local media, NGOs, social platforms, etc., and human resources for community outreach and risk communication are available at all levels | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | C1.2 Social and mobilization strategy and risk communication materials have been disseminated to relevant stakeholders at subnational levels | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | C1.3 Data collection systems have been established for (i) social media listening and rumor management; and (ii) assessing behavioral and social data | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
| C2. Points of delivery | C2.1 Points of delivery, including static and outreach (e.g. health facilities, community centers, by appointments, house-to-house) and associated medical supplies have been identified and sufficiently cover target population areas | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed | [6 empty] | Handwashing stations
|  | C2.2 Monitoring tools such as vaccination cards/certificates, facility-based nominal registers and/or tally sheets, vaccination reports (paper and/or electronic) and analytical tools to monitor progress and coverage among different at-risk categories have been developed | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | C2.3 Adequate and trained human resources, including for safe injection practices, are available in all participating facilities | 1. 30% or less; 2. 30-60%; 3. 60-90%; 4. 90% or more | [10 empty] | Training Per diem Hazard pay for health care workers
|  | C2.4 Delivery protocols have been disseminated and supervisory focal points at each facility identified | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
| C3. Vaccine safety surveillance | C3.1 Protocols for adapting surveillance systems for Vaccine Preventable Diseases and AEFI to conduct surveillance of events attributable to vaccination have been developed and disseminated to surveillance facilities/sites and adequate and trained human resources are available to conduct surveillance of events attributable to vaccination | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | C3.2 AEFI committees have been trained to review COVID-19 Vaccine safety data (e.g., causality assessment of serious AEFI, clusters of AEFI, emerging safety concerns etc.) | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed | [10 empty] | Adverse event from immunization (AEFI) surveillance Training Per diem
| C4. Waste management | C4.1 Waste Management protocols appropriate for COVID-19 and including practices and guidelines on disposal routes have been developed and disseminated | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | C4.2 Appropriate waste management systems are in place in all relevant sites, and adequate trained human resource capacity is available | 1. 30% or less; 2. 30-60%; 3. 60-90%; 4. 90% or more | [6 empty] | Waste management
D. Supporting Systems and Infrastructure | D1. Data quality | D1.1 Appropriate institutional and electronic management systems (medical records, systems entry, immunization cards) that facilitate successful delivery of vaccines are in place to allow timely and accurate reporting on delivery, and adequate and trained human resources are available | 1. 30% or less; 2. 30-60%; 3. 60-90%; 4. 90% or more | [6 empty] | Vaccination certificates
| D2. Infrastructure | D2.1 Inputs related to infrastructure for energy (primary and back-up power), communications (including connectivity) and water are adequately assessed and costed | 1. 30% or less; 2. 30-60%; 3. 60-90%; 4. 90% or more | [6 empty] | Generators Telecom Water Supply

## Comparison of VRAF versions (hidden)
Comparison between version 1 (October 5, 2020) and version 2 (November 4, 2020) of the VRAF
Please note, additions, deletions and changes in version 2 (November 4, 2020) of the VRAF version colored in blue.
Covid-19 Vaccine Readiness Assessment Framework
Core Activity Areas | Assessment Area | Indicators | Status (keep only one of the following) | Administrative, organizational, legislative/regulatory and coordination requirements | [5 empty] | Medical supplies and supporting infrastructure equipment and transport |  |  |  | Human resources and training |  |  |  | Financing
|  |  |  | Central |  |  | Sub-National (Departments, Regions, Districts)
|  |  |  | Brief assessment of current status (Column deleted in version 2 of the VRAF) | What administrative, organizational, regulatory and coordination actions need to be undertaken to get to 'completed' or 'more than 90%' status | What would it cost to undertake the administrative, organizational, regulatory and coordination actions to get to 'completed' or 'more than 90%' status (Column deleted in version 2 of the VRAF) | Brief assessment of current status (Column deleted in in version 2 of the VRAF) | What administrative, organizational, regulatory and coordination actions need to be undertaken to get to 'completed' or 'more than 90%' status | What would it cost to undertake the administrative, organizational, regulatory and coordination actions to get to 'completed' or 'more than 90%' status (Column deleted in in version 2 of the VRAF) | What medical supplies and equipment are needed to get to 'completed' or 'more than 90%' status | What is currently available (Column deleted in in version 2 of the VRAF) | What medical supplies and equipment need to be procured to meet the shortfall (Column deleted in in version 2 of the VRAF) | What would it cost to procure the medical supplies and equipment to get to 'completed' or 'more than 90%' status | What are the staffing and training requirements to get a 'completed' or 'more than 90%' status | What is currently available (Column deleted in in version 2 of the VRAF) | What staff needs to be hired and trained to meet the shortfall (Column deleted in in version 2 of the VRAF) | What would it cost to hire and train staff needed to get to 'completed' or 'more than 90%' status | What is the total financing needed to undertake the administrative actions, procure the medical supplies & equipment, and hire & train staff (and admin costs, if any), to get to a 'completed' or 'more than 90%' status
[6 empty] | X1 (admin costs are still computed in version 2 of the VRAF, but are included only in the Financing column) |  |  | X2 (admin costs are still computed in the November version of the VRAF, but are included only in the Financing column) |  |  |  | X1 (X3 in the older version of the VRAF) |  |  |  | X2 (X4 in the older version of the VRAF) | X1+X2+admin costs if any (Admin costs were computed as X1 and X2 in version 1 of the VRAF, now they are directly included here)
A. Planning and Management | A1. Vaccination objectives and targets | A1.1 Program objectives are defined and agreed by key stakeholders at central and sub-national levels, including representatives of target populations, community leaders, religious leaders, etc., and reflect the epidemiological situation and are adaptable to vaccine supply scenarios (protection of vulnerable populations, continuity of essential services, equity) | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A1.2 Implementing agencies (government or private) have been identified | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A1.3 Priority target population(s) has been identified, enumerated and listed by location | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A1.4 Accountable body and leadership, such as EPI governance and management structure, exist and are functioning | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
| A2. Regulation and Standards | A2.1 Appropriate regulatory measures are in place for approval of COVID-19 vaccines and related supplies | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A2.2 Regulatory measures are in place for procurement of COVID-19 vaccines and related supplies, including domestic and external procurement | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A2.3 Regulatory measures are in place for import of COVID-19 vaccines and related supplies, including for taxes and tariffs | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A2.4 Regulatory measures are in place for data protection, and appropriate data governance regulation is in place to monitor legitimate, appropriate and proportionate use and processing of data which may be routinely collected and managed in health information systems (Indicator not included in version 1 of the VRAF) | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A.2.5. Regulatory capacity to accommodate requests for no-fault liability funds and any related regulatory requirements (if not already in existence) is in place (Indicator not included in version 1 of the VRAF) | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A.2.6 Regulatory measures regarding consent to vaccinations, process for agreeing to or refusing to be vaccinated, and measures to protect those that refuse to be vaccinated are in place (Indicator not included in version 1 of the VRAF) | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A.2.7 Regulatory measures are in place regarding personnel who will be carrying out vaccinations, including all staff/personnel/consultants etc. engaged in such activities (cover military personnel also, if possible), and include requirements relating to chemical, physical and biological substances, not engaging in sexual exploitation and abuse and sexual harassment, participation in training, reporting and non-retaliation (Indicator not included in version 1 of the VRAF) | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A2.8 For delivery through private facilities: Standard Operating Procedures are developed, including a complaints-handling mechanism; mechanisms for certification of facilities is approved, of financing mechanism is developed and a mechanism for and of monitoring of performance and integrity checks are developed and approved; and service quality and performance and reporting standards are agreed | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
| A3. Performance management and M&E | A3.1 A gap analysis of delivery and storage capacity has been conducted, and potential bottlenecks, capacity deficiencies and recommendations for improvement have been identified | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A3.2 Outreach for target populations has been scheduled, necessary planning for locations and logistics has been carried out, and an information awareness program has been designed and is being implemented | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A.3.4 A mechanism with multiple intake points has been designed and is in place, and is operational for feedback and grievances in relation to the vaccine program (Indicator not included in the previous version of the VRAF) | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A3.5 A monitoring & evaluation (M&E) framework for program roll-out has been developed, including for gathering information from facilities participating in vaccine delivery, and the necessary human resource capacity is in place | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
| A4. Budgeting | A4.1 COVID vaccine program costs (vaccine, operating costs, HR and capital costs) have been included in government budgetary and/or planning documents approved by the appropriate authority; in addition, appropriation or allocation (from MOF/treasury) is included in the cash planning as an additional means to ensure that financing is indeed readily available | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | A.4.2 Management aspects of appropriations from the MOF/Treasury are in place (Indicator not included in the previous version of the VRAF) | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
B. Supply and Distribution | B1. Vaccines, PPEs and other medical and non-medical supplies | B1.1 A procurement plan, including costs of items, due diligence mechanisms and purchasing strategies for COVID-19 vaccine(s) and ancillary supplies (syringes, safety boxes), has been developed; budget has been approved; and monitoring arrangements are agreed and updated as needed [if COVID-19 vaccines procurement arrangements have been made or are under discussion, e.g. bilateral purchase arrangements or Advance Purchase Commitments, please mention it here] | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed | [6 empty] | Vaccine (doses) Syringes & safety boxes Other items: alcohol wipes, plasters, cotton swabs, etc.
|  | B1.2 Personal Protective Equipment and IPC equipment needs have been identified for individuals supporting the immunization program, and a procurement plan, including costs of items, and due diligence arrangements have been developed | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed | [6 empty] | PPEs for health care workers: 1. Masks 2. Gowns 3. Face Shields 4. Gloves 5. Boots 6. Sanitizer 7.Handwashing Stations
|  | B1.3 Waste management equipment and supplies has been procured for appropriate implementation of protocols (Indicator not included in the previous version of the VRAF) | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
| B2. Logistics and cold chain | B2.1 A distribution strategy, from points-of-entry to the front-line, including transport, stocking and other components of the supply chain has been developed and operationalized, and the necessary human resource capacity is in place | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | B2.2 Requirement of Cold chain equipment and cold storage infrastructure at participating locations has been determined is in place, and if not, the needs have been identified and a procurement sources identified plan / purchasing strategy for procurement of extra infrastructure is in place or is under discussion | 1. 30% or less; 2. 30-60%; 3. 60-90%; 4. 90% or more | [6 empty] | Refrigerated vehicles Refrigerated Storage Temperature monitoring devices, etc.
|  | B2.3 Systems and protocols for tracking and monitoring the distribution of vaccines and key supplies are in place through the Government's existing Vaccine Logistics Management and Information System (VLMIS) | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
| B3. Waste management (Category C4 in version 1 of the VRAF) | B3.1 Waste Management protocols appropriate for COVID-19, both hazardous and non-hazardous, and including practices and guidelines on disposal routes have been developed and disseminated (Included as indicator C4.1 in version 1 of the VRAF) | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | B3.2 Appropriate waste management systems are in place in all relevant sites, and adequate trained human resource capacity is available (Included as indicator C4.2 in version 1 of the VRAF) | 1. 30% or less; 2. 30-60%; 3. 60-90%; 4. 90% or more
|  | B3.3 Properly-licensed waste management providers (especially for hazardous waste storage, transportation and disposal) are identified and can be operationalized (Indicator not included in the previous version of the VRAF) | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
C. Program Delivery | C1. Community engagement and advocacy | C1.1 Social mobilization, engagement strategy and information awareness program have been designed and developed to generate vaccine acceptance, confidence and demand, including for engaging with national and local media, NGOs, social platforms, etc., and human resources for community outreach and risk communication management that also explains how complaints may be lodged and how they will be resolved, are available at all levels | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | C1.2 Social and mobilization strategy and risk communication materials have been disseminated to relevant stakeholders at subnational levels | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | C1.3 Data collection systems have been established for (i) social media listening and rumor management; and (ii) assessing behavioral and social data | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
| C2. Points of delivery | C2.1 Points of delivery, including static and outreach (e.g., health facilities, community centers, by appointments, house-to-house) and associated medical supplies have been identified and sufficiently cover mapped to target population areas | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | C2.2 Monitoring tools such as vaccination cards/certificates, facility-based nominal registers and/or tally sheets, vaccination reports (paper and/or electronic) and analytical tools to monitor progress and coverage among different at-risk categories have been developed | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | C2.3 Adequate and trained human resources, including for safe injection practices, are available in all participating facilities | 1. 30% or less; 2. 30-60%; 3. 60-90%; 4. 90% or more | [10 empty] | Training Per diem Hazard pay for health care workers
|  | C2.4 Delivery and acceptance protocols have been disseminated, monitoring arrangements are in place, and supervisory focal points at each facility have been identified | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
| C3. Vaccine safety surveillance | C3.1 Protocols for adapting surveillance systems for Vaccine Preventable Diseases and AEFI to conduct surveillance of events attributable to vaccination have been developed and disseminated to surveillance facilities/sites and adequate and trained human resources are available to conduct surveillance of events attributable to vaccination | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
|  | C3.2 AEFI committees have been trained to review COVID-19 Vaccine safety data (e.g., causality assessment of serious AEFI, clusters of AEFI, emerging safety concerns etc.) | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed | [10 empty] | Adverse event from immunization (AEFI) surveillance Training Per diem
|  | C.3.3 Compensation schemes in the event that there are unintended health consequences as result of vaccines have been established (Indicator not included in version 1 of the VRAF) | 1. Not Started; 2. In progress, early stage; 3. In progress, maturity stage; 4. Completed
D. Supporting Systems and Infrastructure | D1. Data quality | D1.1 Appropriate institutional and electronic management systems (medical records, systems entry, immunization cards) that facilitate successful delivery of vaccines are in place to allow timely and accurate reporting on delivery, and adequate and trained human resources are available | 1. 30% or less; 2. 30-60%; 3. 60-90%; 4. 90% or more |  | Vaccine Logistics Management and Information System; Vaccination Certificates
| D2. Infrastructure | D2.1 Inputs related to infrastructure for energy (primary and back-up power), communications (including connectivity) and water are adequately assessed and costed in place | 1. 30% or less; 2. 30-60%; 3. 60-90%; 4. 90% or more | [6 empty] | Generators Water Supply
|  | D.2.2. Appropriate IT Infrastructure, including communications and internet connectivty, is in place (Indicator not included in version 1 of the VRAF) | 1. 30% or less; 2. 30-60%; 3. 60-90%; 4. 90% or more | [6 empty] | Telecom IT Infrastructure – Computers, Cellphones etc.

## VIRAT (hidden)
COVID-19 Vaccine Introduction Readiness Assessment Tool - National Level (Version 21 September 2020)
COUNTRY
Name & Agency of staff completing review
| Fecha de la revisión |  | __/__/__ | __/__/__ | __/__/__ | __/__/__
| Activities (pre-planning activities are shaded in red; yellow cells are the activities that should be completed in the given timeframe) | Pre-Planning activity | Sep-20 (Pre-planning Baseline) | Oct-Nov 20 | Dic 20-ene 21 | Feb-mar 21 | If activity not completed, give reason Provide any other comments, if needed | Action required | Deadline | Person responsible MOH & TA partners (as relevant)
A. PLANIFICACIÓN Y COORDINACIÓN | A.1 Establish (or engage an existing committee) a National Coordinating Committee (NCC) for COVID-19 vaccine introduction with terms of reference, roles and responsibilities and regular meetings | Yes
| A.2 Establish (or engage an existing working group) a National Technical Working Group (NTWG) for COVID-19 vaccine introduction with terms of reference, roles and responsibilities and regular meetings | Yes
A.3 Establish or engage existing NTWG subcommittees, if required, to cover the following workstreams: 1) service delivery 2) vaccine, cold chain & logistics, 3) demand generation & communication (4) prioritization, targeting and COVID-19 surveillance, (5) Monitoring and Evaluation: determination and proof of eligibility, proof of vaccination, monitoring of coverage among at-risk groups, and monitoring of vaccine impact (6) Safety, including injury prevention and AEFI detection and response
A.4 Brief key ministries, NITAG, stakeholders and partners about COVID-19 vaccine introduction and their expected roles
A.5 Inform regularly & disseminate global and regional guidance (i.e. SAGE) with NITAGs & RITAGs and support NITAG working groups on COVID-19 vaccines
A.6 Develop the National Deployment and Vaccination Plan (NDVP) with input from relevant bodies (National COVID-19 Response Coordinating Committee, CNCC, CTWG, NITAG, National Immunization Programme, National Regulatory Authority, AEFI committee and other relevant groups such as private sector). The NDVP should be in line with WHO guidance and SAGE recommendations (plan can be developed by adapting the Pandemic Influenza NDVP, if existing)
A.7 Identify and plan for the national vaccine access/procurement approach (e.g. COVAX Facility, bilateral purchase agreement, procurement through UN agency, self-procurement) and complete required paperwork. (Additional information to follow)
A.8 Review and prepare Government signature for legal agreement to receive Covid-19 vaccine (Additional information to follow)
B. RESOURCES & FUNDING | B.1 Estimate financial and human resources needed (including surge capacity requirements) to conduct the deployment and vaccination operations in the designated points and in the required number of days
B.2 Identify funding mechanisms in collaboration with relevant stakeholders including Inter-Agency Coordinating Committee (ICC), if available at country
B.3 Finalize the budgeted micro-plans for vaccination including plans for other relevant components such as demand generation, risk communications and safety surveillance
B.4 Ensure mechanism to release and distribute funds to lowest levels for operations
C. REGLAMENTACIÓN | C.1 Confirm to WHO the existence of any expedited regulatory pathway for approval of COVID-19 vaccines (i.e. emergency use authorization, exceptional approval/waiver mechanism based on reliance/recognition, abbreviated procedure, fast track, etc.). Time lines and maximum number of days should be mentioned. (expected timeline: maximum 15 working days) | Yes
C.2 Ensure the national regulator or authority has clarified the requirements and documents needed for regulatory approvals of COVID-19 vaccines
C.3 Identify the requirements and documents needed to import COVID-19 vaccines
C.4 Confirm to WHO the existence of an expedited import approval/waiver from appropriate authorities. Time lines and maximum number of days should be mentioned. (expected timeline: maximum 5 working days)
C.5 Ensure a system to waive local lot release testing based on review of summary protocols is in place. Identify the requirements and documents needed for NRA lot release or waiver of lot release for COVID-19 vaccines. Time lines and maximum number of days for lot release/waiver process should be mentioned. (expected timeline: maximum 2 days)
D. PRIORIZACIÓN, FOCALIZACIÓN Y VIGILANCIA DE LA COVID-19 | D.1 Monitor progress of NITAG working groups on COVID-19 vaccines and interim recommendations focusing on prioritization and risk groups | Yes
D.2 Estimate potential numbers of target populations that will be prioritized for access to vaccines stratified by target group and geographic location, i.e. prepare first to define, identify and estimate no. of HCWs
D.3 Coordinate with national COVID-19 disease surveillance group to ensure relevant epidemiological data will be collected to inform planning of subsequent rounds of COVAX vaccination, including outbreak responses
E. Prestación de servicios | E.1 Update protocols for infection prevention and control measures including adequate personal protection equipment (PPE) to minimize exposure risk during immunization sessions | Yes
E.2 Identify potential COVID-19 vaccine delivery strategies leveraging both existing vaccination platforms and non-vaccination delivery approaches to best reach identified target groups
E.3 Identify and develop a master list and strategy of service providers who could effectively deliver COVID-19 vaccine to various target populations
E.4 Ensure availability of plans to safeguard the security of staff (e.g. during an emergency or major campaign) as well as security at the central and/or regional storage facilities and for in-transit of products
F. CAPACITACIÓN Y SUPERVISIÓN | F.1 Develop a training plan to prepare for COVID-19 vaccine introduction that includes key groups of participants, content topic areas, key training partners and training methods (in-person or virtual). WHO will provide a template for guidance | Yes
F.2 Adapt and translate training materials developed by WHO and develop additional training materials as outlined in the training plan
F.3 Conduct virtual and/or in person trainings as outlined in the training plan
G. SEGUIMIENTO Y EVALUACIÓN | G.1 Develop or adapt existing surveillance and monitoring framework with a set of recommended indicators (coverage, acceptability, disease surveillance etc…) for COVID-19 vaccine. Determine whether registration and reporting will be individual or aggregate, and to what extent existing tools and systems can be re-used | Yes
G.2 Develop or adapt necessary monitoring tools or adapt existing tools: vaccination card/certificate - facility-based nominal registers and/or tally sheets, vaccination reports (paper and/or electronic) and analytical tools to monitor progress and coverage among different at-risk categories
G.3 Produce and distribute monitoring tools to eligible vaccination providers, develop, test and roll-out any changes to electronic systems, provide training for use of these tools and processes to traditional and new providers
H. VACCINE, COLD CHAIN & LOGISTICS | H.1 Establish/strengthen the national logistics working group with appropriate terms of reference and standard operating procedures to coordinate COVID-19 vaccines and ancillary products deployment | Yes
H.2 Map key roles and responsibilities needed for vaccine and ancillary products deployment; collect and confirm contact information for key personnel and facilities
H.3 Map the potential port(s) of entry, points of storage (stores), and fallback facilities in the country with their respective cold chain storage (2-8C, -20C, -60/70C) and transportation capacity for vaccines and ancillary products
H.4 Assess dry storage and cold chain capacity at all levels with regards to the COVID-19 vaccines characteristics and fill the identified supply and logistics gaps
H.5 Establish contractual agreements to prepare for vaccine introduction (e.g., vaccine warehousing, transport, waste management, cold chain capacity, etc) where applicable
H.6 Provide standard operating procedures (SOPs) or guidelines for collection and disposal of medical waste to the relevant stakeholders
H.7 Update vaccine stock management tools and operating procedures to reflect the characteristics of COVID-19 vaccines (i.e. vial size, VVM,...)
H.8 Establish security arrangements to ensure the integrity of COVID-19 vaccines and ancillary products throughout the supply chain
I. VIGILANCIA DE LA SEGURIDAD | I.1 Ensure that guidelines, documented procedures and tools for planning and conducting vaccine pharmacovigilance activities (i.e. AEFI reporting, investigation, causality assessment, risk communication and response) are available | Yes
| I.2 Assure competent and trained staff to perform vigilance activities | Yes
| I.3 Expedite training the AEFI committee to review COVID-19 Vaccine safety data (e.g., causality assessment of serious AEFI, clusters of AEFI, emerging safety concerns etc.) | Yes
| I.4 Identify provisions that require manufacturers to implement risk management plans and collect and report COVID-19 vaccine safety data to the NRA | Yes
| I.5 Plan active surveillance of specific COVID-19 vaccine related adverse events. If this is not possible, develop provisions that allow reliance on active surveillance data, decisions, and information from other countries or regional or international bodies | Yes
I.6 Establish a coordination mechanism between relevant stakeholders (NRA, EPI, MAH, MOH, WHO and others) for exchange of COVID-19 Vaccine safety information
I.7 Secure communication channels to share COVID-19 vaccine safety data and findings with relevant regional and international partners
J. GENERACIÓN DE DEMANDA Y COMUNICACIÓN | J.1 Design a demand plan (includes advocacy, communications, social mobilization, risk and safety comms, community engagement, and training) to generate confidence, acceptance and demand for COVID-19 vaccines. Must include a crisis communications preparedness planning | Yes
J.2 Establish data collection systems, including 1) social media listening and rumor management, and 2) assessing behavioral and social data
J.3 Develop key messages and materials for public communications and advocacy, in alignment with demand plan
| Provide overall comment on progress/areas that need attention |  | End Oct 2020
End Nov 2020
End Jan 2021
End Mar 2021